## Prev-FY-Rollng-Prior-1st-Apr-18
Project Number | Actual SD | Revised ED | Group | TRL From | TRL To | Actual TRL From | Actual TRL To | Completed on | Closed On | Program Area | Avg PPI
PA/TAP/679/2015 | 2015-11-07 | 2018-03-31 | PA | 3 | 6 | 3 | 6 | 2018-05-09 | 2019-02-01 | Others | 96
SMC/ABP/719/2016 | 2016-06-29 | 2018-01-31 | SMC | 7 | 7.3 |  |  | 2018-08-07 | 2019-04-04 | Others | 0
SMC/ABP/730/2016 | 2016-05-30 | 2018-02-28 | SMC | 5 | 7.2 | 5 | 7.2 | 2018-04-23 | 2019-04-04 | Others | 100
MCJ/ABP/767/2016 | 2016-07-29 | 2018-03-30 | MCJ | 5 | 7.1 | 5 | 7.1 | 2018-11-09 | 2019-01-14 | Others | 90
SMC/ABP/751/2016 | 2016-08-18 | 2017-11-30 | SMC | 6 | 7.2 | 6 | 7.2 | 2018-08-02 | 2019-01-14 | Others | 50
SMC/ABP/754/2016 | 2016-07-20 | 2017-03-19 | SMC | 6 | 7.2 | 7.1 | 7.3 | 2018-08-08 | 2019-04-04 | Others | 90
MCJ/DEP/827/2016 | 2016-08-22 | 2018-03-31 | MCJ | 2 | 5 | 1 | 4 | 2018-05-15 | 2018-11-08 | Others | 90
MCJ/ABP/807/2016 | 2016-08-31 | 2018-03-30 | MCJ | 4 | 7 | 2 | 5 | 2018-05-15 | 2018-09-12 | Others | 95
PROD/DEP/822/2016 | 2016-08-22 | 2018-02-06 | PROD | 7.3 | 8 | 7 | 7.3 | 2018-04-29 | 2019-03-06 | Others | 90
IM/DEP/859/2016 | 2016-12-09 | 2018-04-08 | IM | 3 | 6 | 2 | 3 | 2018-07-02 | 2019-03-05 | Others | 95
RM/ABP/784/2016 | 2016-09-02 | 2018-02-28 | RM | 5 | 7.1 | 5 | 8 | 2018-04-23 | 2018-06-21 | Others | 89
SMC/ABP/799/2016 | 2017-02-04 | 2017-09-18 | SMC | 7.1 | 7.2 |  |  | 2018-12-18 | 2019-03-06 | Others | 0
ENV/DEP/819/2016 | 2016-10-06 | 2017-11-06 | ENV | 2 | 5 |  |  | 2018-07-10 | 2018-12-14 | Others | 0
ENV/DEP/833/2016 | 2016-10-06 | 2017-10-05 | ENV | 2 | 5 |  |  | 2018-07-10 | 2018-12-14 | Others | 0
IM/ABP/794/2016 | 2016-08-17 | 2019-04-15 | IM | 3 | 7 | 3 | 7.1 | 2019-04-04 | 2019-04-09 | Others | 97
MCJ/DEP/830/2016 | 2016-09-05 | 2017-12-05 | MCJ | 2 | 5 |  |  | 2018-11-09 | 2018-12-12 | Others | 0
SMC/ABP/841/2016 | 2017-01-21 | 2017-07-21 | SMC | 6 | 7.1 |  |  | 2018-04-05 | 2018-06-29 | Others | 0
RM/ABP/853/2016 | 2016-11-28 | 2017-12-31 | RM | 4 | 6 | 5 | 6 | 2018-04-23 | 2018-06-21 | Others | 100
MCJ/DEP/860/2016 | 2016-12-09 | 2018-03-30 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-11-08 | Others | 93
MCJ/ABP/865/2016 | 2017-01-03 | 2018-03-31 | MCJ | 5 | 7.1 | 1 | 7.2 | 2018-05-15 | 2018-11-08 | Others | 100
MMPD/DEP/1007/2018 | 2018-01-29 | 2018-11-30 | MMPD | 3 | 6 | 6 | 7 | 2018-12-06 | 2019-01-30 | Others | 95
MMPD/ABP/861/2016 | 2017-02-15 | 2018-01-31 | MMPD | 6 | 7.1 | 7.1 | 8 | 2018-04-29 | 2019-03-06 | Others | 90
SMC/ABP/858/2016 | 2017-03-01 | 2017-07-30 | SMC | 7 | 7.2 | 7 | 7.1 | 2018-08-07 | 2019-01-31 | Others | 91
MCJ/ABP/864/2016 | 2017-01-30 | 2018-02-28 | MCJ | 6 | 7.1 | 6 | 7.1 | 2018-04-04 | 2018-11-08 | Others | 95
ENV/DEP/879/2017 | 2017-09-05 | 2018-07-24 | ENV | 3 | 4 |  |  | 2018-07-29 | 2018-12-14 | Others | 0
IM/BU/888/2017 | 2017-08-24 | 2018-02-11 | IM | 6 | 7 | 6 | 7 | 2018-10-29 | 2018-11-29 | Others | 95
PROD/DEP/872/2017 | 2017-08-21 | 2018-05-17 | PROD | 3 | 5 |  |  | 2018-08-31 | 2019-03-06 | Others | 0
IM/BU/878/2017 | 2017-08-24 | 2018-05-19 | IM | 7 | 8 | 7 | 7.1 | 2018-10-22 | 2018-12-14 | Others | 95
IM/BU/889/2017 | 2017-08-24 | 2018-05-27 | IM | 7 | 8 | 7 | 7.2 | 2018-11-12 | 2018-11-29 | Others | 100
PROD/DEP/873/2017 | 2017-08-21 | 2018-04-26 | PROD | 3 | 6 | 6 | 7.1 | 2018-05-16 | 2019-03-06 | Others | 90
FAM/BU/893/2017 | 2017-08-09 | 2018-05-27 | FAM | 2 | 8 | 2 | 8 | 2018-06-22 | 2018-08-01 | Others | 90
PROD/DEP/965/2017 | 2017-08-21 | 2018-05-17 | PROD | 5 | 6 | 5 | 6 | 2018-05-16 | 2019-03-06 | Others | 100
PROD/BU/905/2017 | 2017-09-21 | 2018-06-17 | PROD | 3 | 7 |  |  | 2018-08-31 | 2019-03-06 | Others | 0
PROD/BU/927/2017 | 2017-09-19 | 2018-06-15 | PROD | 5 | 6 | 5 | 6 | 2018-05-08 | 2019-03-06 | Others | 95
FAM/DEP/899/2017 | 2017-08-31 | 2018-06-18 | FAM | 2 | 6 | 2 | 6 | 2018-07-06 | 2018-08-01 | Others | 85
IM/BU/900/2017 | 2017-08-24 | 2018-05-20 | IM | 3 | 6 | 3 | 7 | 2018-06-12 | 2018-11-29 | Others | 100
PROD/BU/907/2017 | 2017-08-21 | 2018-05-17 | PROD | 6 | 7.3 |  |  | 2018-05-16 | 2019-03-06 | Others | 0
PROD/DEP/908/2017 | 2017-08-21 | 2018-05-17 | PROD | 5 | 6 | 5 | 6 | 2018-05-16 | 2019-03-06 | Others | 90
MCJ/BU/943/2017 | 2017-08-22 | 2018-05-30 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-06-01 | Others | 96
PROD/BU/909/2017 | 2017-08-23 | 2018-09-30 | PROD | 7.1 | 8 | 7.1 | 8 | 2018-10-05 | 2019-03-06 | Others | 90
MCJ/BU/944/2017 | 2017-09-01 | 2018-05-06 | MCJ | 7.3 | 8 | 7.3 | 7.3 | 2018-05-15 | 2018-11-08 | Others | 91
PROD/BU/911/2017 | 2017-11-01 | 2018-07-28 | PROD | 3 | 7.3 | 7.3 | 7.3 | 2018-04-29 | 2019-02-20 | Others | 95
MCJ/BU/945/2017 | 2017-08-09 | 2018-05-04 | MCJ | 5 | 7.1 | 5 | 6 | 2018-05-15 | 2018-11-08 | Others | 91
SMC/BU/901/2017 | 2017-08-31 | 2018-04-16 | SMC | 7 | 7.3 | 7 | 7 | 2018-04-27 | 2019-04-01 | Others | 75
FAM/DEP/918/2017 | 2017-08-18 | 2018-05-08 | FAM | 3 | 5 | 3 | 5 | 2018-07-09 | 2018-08-01 | Others | 85
SE/TAP/916/2017 | 2017-09-05 | 2018-06-05 | SE | 4 | 5 | 4 | 6 | 2018-04-13 | 2019-02-13 | Others | 97
CCM/BU/919/2017 | 2017-09-20 | 2018-12-20 | CCM | 3 | 7.1 | 3 | 7 | 2019-01-28 | 2019-02-18 | Others | 92
CCM/DEP/921/2017 | 2017-08-21 | 2018-11-21 | CCM | 1 | 5 | 1 | 5 | 2018-11-22 | 2019-02-18 | Others | 90
SMC/BU/974/2017 | 2017-10-31 | 2018-05-15 | SMC | 7 | 7.3 | 7 | 7.3 | 2018-04-13 | 2019-01-14 | Others | 100
SMC/BU/923/2017 | 2017-08-31 | 2018-03-30 | SMC | 7 | 7.2 | 7 | 7.2 | 2018-06-26 | 2018-07-25 | Others | 97
FAM/BU/926/2017 | 2017-08-30 | 2018-06-10 | FAM | 3 | 7.1 | 3 | 7.1 | 2019-02-19 | 2019-04-05 | Others | 95
RM/BU/977/2017 | 2017-10-09 | 2018-06-05 | RM | 6 | 7.1 | 7.1 | 8 | 2018-12-27 | 2019-01-04 | Others | 97
SE/BU/939/2017 | 2017-10-04 | 2018-07-04 | SE | 7.1 | 7.3 | 7.1 | 7.2 | 2018-07-24 | 2019-03-06 | Others | 95
SE/BU/998/2017 | 2017-11-09 | 2018-05-25 | SE | 3 | 7.1 | 3 | 7.2 | 2018-04-13 | 2018-06-29 | Others | 90
NDTS/DEP/966/2017 | 2017-08-28 | 2018-10-31 | NDTS | 2 | 5 | 2 | 5 | 2018-11-07 | 2019-02-21 | Others | 100
MCJ/BU/986/2017 | 2017-12-22 | 2018-08-01 | MCJ | 7.1 | 7.3 | 7.1 | 7.2 | 2018-09-12 | 2018-11-08 | Others | 90
MCJ/BU/950/2017 | 2017-11-09 | 2018-07-26 | MCJ | 3 | 6 | 3 | 6 | 2018-05-15 | 2018-11-08 | Others | 92
MCJ/BU/952/2017 | 2017-09-01 | 2018-05-08 | MCJ | 6 | 7.2 | 6 | 7.2 | 2018-05-15 | 2018-11-08 | Others | 96
MCJ/DEP/951/2017 | 2017-08-31 | 2018-04-21 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-11-08 | Others | 100
PROD/DEP/978/2017 | 2017-09-21 | 2018-05-21 | PROD | 2 | 6 | 2 | 6 | 2018-05-16 | 2019-03-06 | Others | 100
SMC/BU/980/2017 | 2017-10-13 | 2018-04-27 | SMC | 7 | 7.3 | 7 | 7.3 | 2018-04-04 | 2018-05-02 | Others | 98
CCM/BU/961/2017 | 2017-08-24 | 2018-05-08 | CCM | 4 | 8 | 4 | 8 | 2018-06-21 | 2018-11-29 | Others | 75
CCM/TAP/959/2017 | 2017-08-09 | 2018-04-08 | CCM | 3 | 5 | 3 | 4 | 2018-04-03 | 2019-03-22 | Others | 95
SMC/BU/981/2017 | 2017-11-02 | 2018-04-19 | SMC | 7 | 7.3 | 6 | 7.3 | 2018-05-17 | 2018-06-29 | Others | 100
SE/TAP/990/2017 | 2017-11-02 | 2018-11-30 | SE | 7.1 | 7.3 | 7.1 | 7.3 | 2018-11-28 | 2019-02-12 | Others | 98
SMC/BU/995/2017 | 2017-10-16 | 2018-03-31 | SMC | 7 | 7.2 | 6 | 7.1 | 2018-04-27 | 2018-06-08 | Others | 5
PROD/BU/984/2017 | 2017-10-11 | 2018-04-19 | PROD | 5 | 8 | 6 | 7 | 2018-04-29 | 2019-03-06 | Others | 90
SE/TAP/991/2017 | 2017-11-02 | 2018-10-31 | SE | 4 | 5 | 4 | 5 | 2019-01-10 | 2019-02-12 | Others | 96
SE/BU/989/2017 | 2017-11-02 | 2018-05-02 | SE | 8 | 8 | 8 | 8 | 2018-05-14 | 2018-06-29 | Others | 95
MCJ/DEP/1001/2017 | 2018-01-19 | 2018-06-18 | MCJ | 5 | 7.1 | 3 | 4 | 2018-08-03 | 2018-11-08 | Others | 85
NDTS/BU/993/2017 | 2017-10-06 | 2018-04-05 | NDTS | 7.1 | 7.2 | 7.1 | 7.2 | 2018-05-11 | 2018-08-07 | Others | 100
PROD/BU/1006/2018 | 2018-02-20 | 2019-01-31 | PROD | 6 | 7 | 7 | 7.3 | 2019-02-11 | 2019-04-01 | Others | 100
PROD/DEP/1003/2017 | 2018-01-10 | 2018-08-02 | PROD | 1 | 6 | 1 | 5 | 2018-07-05 | 2019-03-06 | Others | 100
SMC/BU/1010/2018 | 2018-03-03 | 2018-05-03 | SMC | 7.1 | 7.2 | 7.1 | 7.2 | 2018-04-05 | 2018-06-08 | Others | 70
IFA/ABP/517/2014 | 2014-08-01 | 2016-03-31 | FAM | 1 | 5 |  |  | 2018-08-13 | 2018-09-07 | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS | 0
IFA/TAP/520/2014 | 2014-08-05 | 2016-03-31 | FAM | 6 | 7.2 |  |  | 2018-07-30 | 2018-09-07 | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS | 0
PROD/DEP/573/2015 | 2015-06-20 | 2016-03-20 | PROD | 3 | 5 |  |  | 2018-08-01 | 2019-03-06 | AUTOMOTIVE | 0
SMC/ABP/637/2015 | 2015-09-02 | 2016-04-02 | SMC | 6 | 7 | 6 | 7 | 2018-04-04 | 2018-07-02 | STEELMAKING AND CASTING | 90
PROD/ABP/661/2015 | 2015-12-11 | 2017-11-30 | PROD | 2 | 5 | 2 | 5 | 2018-06-18 | 2019-03-06 | Others | 90
SMC/DEP/677/2015 | 2015-11-24 | 2016-10-31 | SMC | 5 | 5 |  |  | Yes('18-DEC-2018') |  | Others
PA/DEP/681/2015 | 2015-12-19 | 2018-06-30 | PA | 5 | 7.1 | 1 | 3 | Yes('09-MAY-2018') |  | Others
PA/TAP/680/2015 | 2015-12-19 | 2018-04-30 | PA | 3 | 7.1 | 1 | 6 | Yes('09-JUL-2018') |  | Others
RM/ABP/673/2015 | 2016-02-03 | 2016-09-02 | RM | 4 | 6 |  |  | Yes('07-JAN-2019') |  | Others
ENV/ABP/691/2015 | 2016-01-05 | 2019-03-31 | ENV | 6 | 7 |  |  | Yes('18-MAR-2019') |  | Others
PA/DEP/726/2016 | 2016-06-27 | 2017-08-11 | PA | 3 | 5 |  |  | Yes('09-MAY-2018') |  | Others
ENV/TAP/729/2016 | 2016-09-20 | 2018-09-19 | ENV | 3 | 7 |  |  | Yes('20-SEP-2018') |  | Others
AGGLO/ABP/791/2016 | 2016-09-06 | 2017-09-05 | AGGLO | 3 | 6 |  |  | Yes('21-AUG-2018') |  | Others
IM/ABP/739/2016 | 2016-08-02 | 2019-03-15 | IM | 3 | 4 |  |  | Yes('04-APR-2019') |  | Others
MCJ/ABP/772/2016 | 2016-07-22 | 2018-01-31 | MCJ | 5 | 7.1 |  |  | Yes('15-MAY-2018') |  | Others
PA/DEP/763/2016 | 2016-07-18 | 2018-03-23 | PA | 4 | 6 |  |  | Yes('09-MAY-2018') |  | Others
SMC/ABP/749/2016 | 2017-08-02 | 2018-05-18 | SMC | 6 | 7.1 |  |  | Yes('18-DEC-2018') |  | Others
PROD/ABP/762/2016 | 2016-07-19 | 2017-07-31 | PROD | 6 | 7.1 | 6 | 7.1 | Yes('29-APR-2018') |  | Others
SMC/ABP/753/2016 | 2016-11-24 | 2017-08-08 | SMC | 7 | 7.3 |  |  | Yes('18-DEC-2018') |  | Others
PA/ABP/803/2016 | 2016-09-30 | 2017-12-07 | PA | 7 | 8 | 7 | 8 | Yes('09-MAY-2018') |  | Others
PA/DEP/825/2016 | 2016-09-05 | 2018-03-31 | PA | 3 | 7 | 6 | 7.1 | Yes('09-MAY-2018') |  | Others
PA/ABP/804/2016 | 2016-09-27 | 2018-03-31 | PA | 5 | 7.3 | 5 | 7.3 | Yes('09-MAY-2018') |  | Others
NDTS/DEP/832/2016 | 2016-09-05 | 2018-01-31 | NDTS | 2 | 7.1 | 6 | 7.2 | Yes('09-OCT-2018') |  | Others
PROD/ABP/851/2016 | 2016-11-03 | 2019-02-28 | PROD | 5 | 6 |  |  | Yes('01-MAR-2019') |  | Others
ENV/ABP/863/2016 | 2016-12-06 | 2018-03-31 | ENV | 5 | 6 |  |  | Yes('29-APR-2018') |  | Others
PA/ABP/868/2016 | 2017-02-14 | 2017-12-31 | PA | 5 | 7 |  |  | Yes('13-FEB-2019') |  | Others
ENV/ABP/870/2017 | 2017-03-14 | 2019-03-31 | ENV | 5 | 6 |  |  | Yes('03-NOV-2018') |  | Others
ENV/TAP/871/2017 | 2017-05-10 | 2018-06-06 | ENV | 5 | 7 |  |  | Yes('09-JUL-2018') |  | Others
PROD/BU/967/2017 | 2017-10-09 | 2018-07-05 | PROD | 6 | 8 | 5 | 7 | Yes('06-DEC-2018') |  | Others
ENV/BU/881/2017 | 2017-08-09 | 2018-06-27 | ENV | 7.1 | 8 |  |  | Yes('29-APR-2018') |  | Others
PROD/DEP/875/2017 | 2017-10-05 | 2019-02-04 | PROD | 5 | 6 | 5 | 6 | Yes('11-FEB-2019') |  | Others
RM/BU/896/2017 | 2017-09-06 | 2018-06-22 | RM | 3 | 6 |  |  | Yes('11-OCT-2018') |  | Others
RM/TAP/885/2017 | 2017-08-09 | 2018-05-25 | RM | 1 | 3 | 5 | 6 | Yes('28-NOV-2018') |  | Others
RM/TAP/897/2017 | 2017-08-21 | 2018-06-06 | RM | 3 | 5 |  |  | Yes('08-JAN-2019') |  | Others
PA/DEP/955/2017 | 2017-09-21 | 2018-06-24 | PA | 3 | 5 | 3 | 5 | Yes('09-MAY-2018') |  | Others
MCJ/BU/964/2017 | 2017-08-17 | 2018-11-30 | MCJ | 7.1 | 8 | 7.1 | 8 | Yes('11-DEC-2018') |  | Others
SE/DEP/914/2017 | 2017-09-05 | 2018-06-05 | SE | 2 | 5 | 2 | 5 | Yes('25-JUN-2018') |  | Others
PA/BU/956/2017 | 2017-11-14 | 2018-08-17 | PA | 6 | 7.3 | 6 | 7.3 | Yes('09-MAY-2018') |  | Others
PROD/BU/910/2017 | 2017-08-31 | 2018-11-30 | PROD | 5 | 6 | 6 | 7.3 | Yes('06-DEC-2018') |  | Others
PROD/DEP/912/2017 | 2017-08-21 | 2018-11-16 | PROD | 3 | 6 | 4 | 6 | Yes('06-DEC-2018') |  | Others
MCJ/BU/946/2017 | 2017-08-09 | 2018-04-30 | MCJ | 6 | 7.2 |  |  | Yes('09-NOV-2018') |  | Others
SE/DEP/915/2017 | 2017-09-05 | 2018-05-27 | SE | 3 | 5 | 3 | 6 | Yes('13-APR-2018') |  | Others
SE/DEP/970/2017 | 2017-08-31 | 2018-05-31 | SE | 3 | 5 |  |  | Yes('13-APR-2018') |  | Others
SE/DEP/936/2017 | 2017-08-21 | 2018-10-31 | SE | 3 | 5 |  |  | Yes('09-NOV-2018') |  | Others
RM/DEP/904/2017 | 2017-09-21 | 2018-07-07 | RM | 3 | 5 |  |  | Yes('10-AUG-2018') |  | Others
CCM/DEP/922/2017 | 2017-09-21 | 2018-09-20 | CCM | 1 | 5 |  |  | Yes('03-APR-2018') |  | Others
PA/BU/969/2017 | 2017-09-19 | 2018-06-22 | PA | 6 | 8 | 6 | 8 | Yes('09-MAY-2018') |  | Others
SMC/DEP/934/2017 | 2018-01-12 | 2018-09-11 | SMC | 6 | 6 |  |  | Yes('15-OCT-2018') |  | Others
SE/DEP/937/2017 | 2017-08-31 | 2018-12-31 | SE | 2 | 5 |  |  | Yes('10-JAN-2019') |  | Others
NDTS/BU/941/2017 | 2017-08-04 | 2018-06-30 | NDTS | 3 | 7 | 7 | 7.3 | Yes('29-JUN-2018') |  | Others
PROD/DEP/913/2017 | 2017-08-18 | 2018-05-13 | PROD | 3 | 6 | 5 | 6 | Yes('16-MAY-2018') |  | Others
SE/BU/938/2017 | 2017-09-06 | 2018-10-08 | SE | 3 | 7.1 |  |  | Yes('28-NOV-2018') |  | Others
SE/BU/940/2017 | 2017-08-23 | 2018-05-07 | SE | 3 | 7.1 | 3 | 4 | Yes('28-MAY-2018') |  | Others
CCM/DEP/960/2017 | 2017-08-16 | 2018-08-15 | CCM | 1 | 5 |  |  | Yes('20-AUG-2018') |  | Others
PROD/DEP/979/2017 | 2017-11-02 | 2018-12-31 | PROD | 2 | 5 | 6 | 8 | Yes('11-FEB-2019') |  | Others
PROD/DEP/983/2017 | 2017-11-02 | 2019-01-31 | PROD | 2 | 6 | 2 | 6 | Yes('11-FEB-2019') |  | Others
SMC/BU/996/2017 | 2017-10-16 | 2018-03-31 | SMC | 7 | 7.2 | 7 | 7.2 | Yes('15-MAR-2019') |  | Others
SE/BU/999/2017 | 2018-02-20 | 2019-03-15 | SE | 7.1 | 8 |  |  | Yes('21-MAR-2019') |  | Others
SE/DEP/988/2017 | 2017-11-02 | 2018-05-18 | SE | 5 | 6 | 5 | 5 | Yes('13-APR-2018') |  | Others
RC/ABP/458/2014 | 2014-09-12 | 2015-03-14 | RM | 2 | 5 |  |  | Yes('04-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
RC/DEP/466/2014 | 2014-07-31 | 2016-07-31 | RM | 3 | 6 |  |  | Yes('04-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
RC/ABP/529/2014 | 2014-10-28 | 2016-03-31 | RM | 4 | 5 |  |  | Yes('21-JUN-2018') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
CCM/TAP/557/2015 | 2015-04-10 | 2017-12-31 | CCM | 1 | 7.1 |  |  | Yes('05-NOV-2018') |  | AGGLOMERATION AND IRON MAKING
RM/TAP/652/2015 | 2015-11-10 | 2017-03-31 | RM | 1 | 4 |  |  | Yes('27-DEC-2018') |  | Others
MCJ/TAP/609/2015 | 2015-07-22 | 2017-04-21 | RM | 3 | 4 |  |  | Yes('16-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
SMC/ABP/615/2015 | 2015-09-19 | 2016-03-06 | SMC | 6 | 7 |  |  | Yes('14-DEC-2018') |  | STEELMAKING AND CASTING
NDTS/DEP/834/2016 | 2016-10-07 | 2018-12-31 | NDTS | 2 | 7.1 |  |  |  |  | Others
IM/DEP/740/2016 | 2016-07-28 | 2019-02-28 | IM | 3 | 5 |  |  |  |  | Others
MMPD/ABP/844/2016 | 2017-04-21 | 2017-11-10 | MMPD | 2 | 7.1 |  |  |  |  | Others
FAM/BU/973/2017 | 2017-09-18 | 2018-12-31 | FAM | 3 | 5 |  |  |  |  | Others
PA/DEP/954/2017 | 2017-08-21 | 2019-02-28 | PA | 3 | 6 |  |  |  |  | Others
FAM/DEP/886/2017 | 2017-08-25 | 2018-12-15 | FAM | 3 | 7.2 |  |  |  |  | Others
ENV/BU/877/2017 | 2017-09-18 | 2019-08-18 | ENV | 4 | 6 |  |  |  |  | Others
ENV/TAP/883/2017 | 2017-09-04 | 2019-02-28 | ENV | 3 | 4 |  |  |  |  | Others
IM/DEP/892/2017 | 2017-08-09 | 2019-02-28 | IM | 3 | 5 |  |  |  |  | Others
NDTS/BU/1005/2018 | 2018-02-07 | 2019-05-31 | NDTS | 7 | 8 |  |  |  |  | Others
PROD/BU/906/2017 | 2017-08-23 | 2018-11-30 | PROD | 7.1 | 7.3 |  |  |  |  | Others
RM/TAP/894/2017 | 2017-08-31 | 2019-03-18 | RM | 7.1 | 7.3 |  |  |  |  | Others
RM/TAP/880/2017 | 2017-08-09 | 2020-01-31 | RM | 3 | 7.1 |  |  |  |  | Others
IM/DEP/895/2017 | 2017-08-21 | 2019-02-15 | IM | 3 | 5 |  |  |  |  | Others
ENV/TAP/903/2017 | 2017-08-31 | 2019-05-31 | ENV | 3 | 4 |  |  |  |  | Others
MCJ/BU/947/2017 | 2017-10-23 | 2018-06-28 | MCJ | 6 | 7.1 |  |  |  |  | Others
RM/BU/925/2017 | 2017-08-10 | 2018-05-10 | RM | 3 | 6 |  |  |  |  | Others
CCM/BU/930/2017 | 2017-08-31 | 2018-06-16 | CCM | 3 | 7.1 |  |  |  |  | Others
ENV/BU/972/2017 | 2017-10-01 | 2018-12-31 | ENV | 7.1 | 7.3 |  |  |  |  | Others
MCJ/BU/987/2017 | 2017-11-10 | 2019-03-31 | MCJ | 5 | 7 |  |  |  |  | Others
PA/DEP/874/2017 | 2017-08-21 | 2019-02-28 | PA | 3 | 6 |  |  |  |  | Others
FAM/TAP/935/2017 | 2017-08-30 | 2018-05-14 | FAM | 7 | 7 |  |  |  |  | Others
MCJ/BU/968/2017 | 2017-09-01 | 2018-12-31 | MCJ | 5 | 7 |  |  |  |  | Others
MCJ/BU/953/2017 | 2017-09-01 | 2019-02-28 | MCJ | 5 | 7.1 |  |  |  |  | Others
SE/BU/992/2017 | 2017-12-06 | 2019-03-30 | SE | 5 | 7.1 |  |  |  |  | Others
FAM/BU/958/2017 | 2017-09-01 | 2019-05-16 | FAM | 3 | 6 |  |  |  |  | Others
RC-PCAC/DEP/1002/2017 | 2018-01-10 | 2018-07-10 | RC-PCAC | 3 | 5 |  |  |  |  | Others
MCJ/BU/1004/2017 | 2018-02-28 | 2019-02-28 | MCJ | 5 | 7 |  |  |  |  | Others
PROD/BU/1008/2018 | 2018-02-19 | 2018-06-18 | PROD | 6 | 7.3 |  |  |  |  | MILLS PROCESSES
RC/DEP/540/2014 | 2015-02-03 | 2016-05-31 | RM | 4 | 5 |  |  |  |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS

## FY-19-Started
Project Number | Actual SD | Revised ED | Group | TRL From | TRL To | Actual TRL From | Actual TRL To | Completed on | Closed On | Program Area | Avg PPI
SMC/BU/1011/2018 | 2018-04-24 | 2018-07-27 | SMC | 7 | 7.2 | 7 | 7.2 | 2018-08-02 | 2018-11-28 | Others | 100
IM/BU/1059/2018 | 2018-05-02 | 2019-02-28 | IM | 4 | 7.1 | 4 | 8 | 2019-03-20 | 2019-03-22 | Others | 90
SE/BU/1065/2018 | 2018-05-21 | 2019-03-28 | SE | 2 | 5 | 2 | 8 | 2019-02-26 | 2019-04-04 | Others | 95
SE/BU/1014/2018 | 2018-06-11 | 2019-04-18 | SE | 2 | 7 | 2 | 6 | 2019-02-26 | 2019-04-04 | Others | 97
AGGLO/TAP/1031/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 90
AGGLO/TAP/1045/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 100
AGGLO/DEP/1053/2018 | 2018-06-04 | 2019-02-18 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-18 | 2019-02-19 | Others | 95
IM/BU/1061/2018 | 2018-06-07 | 2019-03-23 | IM | 7 | 8 | 4 | 7 | 2019-03-19 | 2019-03-20 | Others | 100
AGGLO/DEP/1057/2018 | 2018-05-30 | 2019-02-13 | AGGLO | 2 | 3 | 2 | 3 | 2019-02-13 | 2019-02-18 | Others | 95
IM/BU/1060/2018 | 2018-05-02 | 2019-02-15 | IM | 4 | 6 | 4 | 6 | 2019-03-19 | 2019-03-20 | Others | 97
ENV/BU/1092/2018 | 2018-07-24 | 2019-02-11 | ENV | 7 | 8 | 4 | 7 | 2019-02-10 | 2019-02-12 | Others | 95
AGGLO/TAP/1087/2018 | 2018-06-20 | 2019-04-05 | AGGLO | 3 | 5 | 3 | 5 | 2019-02-15 | 2019-02-18 | Others | 100
ENV/TAP/1148/2018 | 2018-12-07 | 2020-06-08 | ENV | 6 | 7 | 4 | 7.1 | 2019-02-12 | 2019-02-15 | Others | 100
SE/BU/997/2017 | 2018-07-24 | 2019-02-06 | SE | 7.1 | 7.3 |  |  | Yes('26-FEB-2019') |  | Others
NDTS/BU/1000/2017 | 2018-10-10 | 2019-07-10 | NDTS | 6 | 7.3 |  |  | NO |  | Others
NDTS/DEP/942/2017 | 2018-07-11 | 2019-07-07 | NDTS | 1 | 6 |  |  | NO |  | Others
SMC/BU/962/2017 | 2018-05-28 | 2019-01-25 | SMC | 6 | 6 |  |  | Yes('06-MAR-2019') |  | Others
PROD/BU/1068/2018 | 2018-06-11 | 2018-12-11 | PROD | 6 | 8 |  |  | NO |  | Others
FAM/BU/1012/2018 | 2018-04-24 | 2018-12-24 | FAM | 3 | 6 |  |  | NO |  | Others
NDTS/BU/1072/2018 | 2018-06-04 | 2019-02-28 | NDTS | 3 | 7 |  |  | NO |  | Others
SMC/DEP/1013/2018 | 2018-05-11 | 2019-02-28 | SMC | 7 | 7.2 |  |  | Yes('04-APR-2019') |  | Others
NDTS/DEP/1071/2018 | 2018-06-04 | 2019-04-05 | NDTS | 3 | 7.1 | 3 | 7.2 | Yes('22-FEB-2019') |  | Others
ENV/TAP/1022/2018 | 2018-05-30 | 2019-05-25 | ENV | 7 | 8 |  |  | NO |  | Others
PROD/BU/1073/2018 | 2018-05-15 | 2019-03-14 | PROD | 3 | 7.3 |  |  | NO |  | Others
PROD/BU/1171/2018 | 2018-10-11 | 2019-06-09 | PROD | 3 | 6 |  |  | NO |  | Others
MCJ/BU/1127/2018 | 2018-11-08 | 2019-08-11 | MCJ | 6 | 7.1 |  |  | NO |  | Others
PROD/DEP/1082/2018 | 2018-09-21 | 2019-07-20 | PROD | 5 | 7 |  |  | NO |  | Others
ENV/DEP/1023/2018 | 2018-05-11 | 2019-05-06 | ENV | 5 | 7 |  |  | NO |  | Others
ENV/DEP/1024/2018 | 2018-05-23 | 2019-05-18 | ENV | 4 | 6 |  |  | Yes('27-MAR-2019') |  | Others
ENV/BU/1159/2018 | 2018-10-08 | 2019-05-07 | ENV | 6 | 7 |  |  | NO |  | Others
ENV/DEP/1026/2018 | 2018-05-30 | 2019-05-20 | ENV | 3 | 5 |  |  | NO |  | Others
ENV/DEP/1027/2018 | 2018-05-30 | 2019-05-20 | ENV | 3 | 5 |  |  | Yes('25-MAR-2019') |  | Others
ENV/DEP/1019/2018 | 2018-06-18 | 2019-06-08 | ENV | 6 | 7 |  |  | NO |  | Others
ENV/BU/1029/2018 | 2018-06-04 | 2019-05-26 | ENV | 5 | 6 |  |  | NO |  | Others
RM/BU/1030/2018 | 2018-07-02 | 2019-04-18 | RM | 5 | 7.1 |  |  | NO |  | Others
SMC/BU/1121/2018 | 2018-07-06 | 2019-03-24 | SMC | 6 | 7.3 |  |  | Yes('03-APR-2019') |  | Others
AGGLO/TAP/1033/2018 | 2018-05-30 | 2019-03-16 | AGGLO | 5 | 7.1 |  |  | NO |  | Others
ENV/BU/1034/2018 | 2018-08-03 | 2019-07-29 | ENV | 6 | 7 |  |  | NO |  | Others
IM/BU/1103/2018 | 2018-08-03 | 2019-05-09 | IM | 7 | 7.2 |  |  | NO |  | Others
IM/BU/1104/2018 | 2018-09-11 | 2019-05-18 | IM | 7.1 | 7.3 |  |  | Yes('21-MAR-2019') |  | Others
RM/BU/1125/2018 | 2018-08-10 | 2020-02-24 | RM | 4 | 5 |  |  | NO |  | Others
CCM/DEP/1035/2018 | 2018-05-11 | 2019-03-21 | CCM | 1 | 4 |  |  | NO |  | Others
RM/DEP/1036/2018 | 2018-06-05 | 2019-03-06 | RM | 3 | 4 |  |  | NO |  | Others
CCM/TAP/1037/2018 | 2018-04-25 | 2019-03-05 | CCM | 4 | 6 |  |  | NO |  | Others
CCM/TAP/1038/2018 | 2018-05-11 | 2019-03-26 | CCM | 4 | 6 |  |  | NO |  | Others
CCM/BU/1040/2018 | 2018-04-19 | 2019-03-04 | CCM | 5 | 7.1 |  |  | NO |  | Others
RM/BU/1109/2018 | 2018-07-25 | 2020-01-24 | RM | 3 | 7 |  |  | NO |  | Others
FAM/BU/1041/2018 | 2018-06-19 | 2019-07-09 | FAM | 3 | 6 |  |  | NO |  | Others
RM/DEP/1042/2018 | 2018-05-30 | 2019-04-28 | RM | 3 | 4 |  |  | NO |  | Others
RM/DEP/1044/2018 | 2018-06-28 | 2019-03-27 | RM | 3 | 4 |  |  | NO |  | Others
CCM/DEP/1020/2018 | 2018-05-11 | 2019-03-26 | CCM | 3 | 5 |  |  | NO |  | Others
SE/DEP/1063/2018 | 2018-09-10 | 2020-05-10 | SE | 4 | 7.3 |  |  | NO |  | Others
RM/TAP/1055/2018 | 2018-09-10 | 2019-07-10 | RM | 4 | 6 |  |  | NO |  | Others
CCM/DEP/1047/2018 | 2018-04-25 | 2019-03-10 | CCM | 1 | 5 |  |  | NO |  | Others
RM/TAP/1048/2018 | 2018-06-18 | 2019-05-02 | RM | 6 | 7 |  |  | NO |  | Others
SMC/BU/1114/2018 | 2018-06-27 | 2019-03-28 | SMC | 7.1 | 7.3 |  |  | Yes('04-MAR-2019') |  | Others
AGGLO/BU/1049/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 3 | 6 |  |  | Yes('01-APR-2019') |  | Others
AGGLO/DEP/1052/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 |  |  | NO |  | Others
RM/BU/1110/2018 | 2018-07-27 | 2019-04-27 | RM | 5 | 7.2 |  |  | NO |  | Others
RM/TAP/1051/2018 | 2018-05-30 | 2019-04-18 | RM | 3 | 4 |  |  | NO |  | Others
AGGLO/BU/1084/2018 | 2018-07-04 | 2019-03-05 | AGGLO | 4 | 6 |  |  | NO |  | Others
AGGLO/DEP/1054/2018 | 2018-06-06 | 2019-04-20 | AGGLO | 3 | 6 |  |  | NO |  | Others
PROD/DEP/1079/2018 | 2018-12-24 | 2019-10-23 | PROD | 3 | 6 |  |  | NO |  | Others
PROD/DEP/1064/2018 | 2018-06-28 | 2019-04-27 | PROD | 2 | 6 |  |  | Yes('01-APR-2019') |  | Others
AGGLO/DEP/1085/2018 | 2018-06-28 | 2019-05-14 | AGGLO | 3 | 5 |  |  | NO |  | Others
FAM/DEP/1050/2018 | 2018-08-06 | 2019-07-26 | FAM | 4 | 5 |  |  | NO |  | Others
SMC/DEP/1142/2018 | 2018-10-31 | 2019-04-17 | SMC | 6 | 6 |  |  | Yes('28-MAR-2019') |  | Others
IM/DEP/1105/2018 | 2018-08-02 | 2019-05-01 | IM | 4 | 6 |  |  | NO |  | Others
ENV/DEP/1089/2018 | 2018-09-10 | 2019-06-19 | ENV | 5 | 6 |  |  | NO |  | Others
SMC/DEP/1116/2018 | 2018-08-03 | 2019-05-05 | SMC | 5 | 6 |  |  | Yes('01-APR-2019') |  | Others
SMC/BU/1117/2018 | 2018-08-02 | 2019-02-17 | SMC | 7 | 7.3 |  |  | NO |  | Others
CCM/DEP/1058/2018 | 2018-04-25 | 2019-03-10 | CCM | 2 | 5 |  |  | NO |  | Others
ENV/BU/1090/2018 | 2018-08-06 | 2019-08-28 | ENV | 6 | 7 |  |  | NO |  | Others
FAM/TAP/1097/2018 | 2018-08-06 | 2019-08-28 | FAM | 5 | 6 |  |  | NO |  | Others
ENV/DEP/1091/2018 | 2018-07-27 | 2019-06-05 | ENV | 5 | 6 |  |  | NO |  | Others
PROD/BU/1080/2018 | 2018-05-30 | 2019-03-29 | PROD | 3 | 7.2 |  |  | NO |  | Others
PROD/DEP/1070/2018 | 2018-05-30 | 2019-09-30 | PROD | 3 | 6 |  |  | NO |  | Others
PROD/BU/1069/2018 | 2018-06-26 | 2019-04-25 | PROD | 6 | 8 |  |  | NO |  | Others
PROD/BU/1075/2018 | 2018-08-28 | 2019-06-26 | PROD | 7.1 | 7.3 |  |  | Yes('01-APR-2019') |  | Others
SE/BU/1067/2018 | 2018-05-21 | 2019-03-19 | SE | 2 | 6 | 2 | 6 | Yes('26-FEB-2019') |  | Others
SMC/BU/1118/2018 | 2018-07-06 | 2019-02-21 | SMC | 7 | 7.3 |  |  | Yes('06-MAR-2019') |  | Others
PROD/DEP/1074/2018 | 2018-05-30 | 2019-03-28 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others
PROD/DEP/1076/2018 | 2018-09-10 | 2019-07-09 | PROD | 4 | 6 |  |  | Yes('01-APR-2019') |  | Others
NDTS/BU/1161/2018 | 2018-10-26 | 2019-07-04 | NDTS | 5 | 7.3 |  |  | NO |  | Others
SE/DEP/1066/2018 | 2018-05-30 | 2019-03-28 | SE | 3 | 5 |  |  | NO |  | Others
PA/BU/1129/2018 | 2019-02-08 | 2019-11-07 | PA | 7.1 | 8 |  |  | NO |  | Others
PROD/BU/1077/2018 | 2018-06-22 | 2019-04-20 | PROD | 6 | 7.1 |  |  | NO |  | Others
PA/BU/1131/2018 | 2018-09-19 | 2019-07-05 | PA | 7 | 8 |  |  | NO |  | Others
PROD/BU/1081/2018 | 2018-12-12 | 2019-10-10 | PROD | 6 | 7 |  |  | NO |  | Others
MCJ/DEP/1133/2018 | 2018-07-23 | 2019-05-08 | MCJ | 4 | 6 |  |  | NO |  | Others
MCJ/BU/1134/2018 | 2018-09-25 | 2019-06-28 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1162/2018 | 2018-10-31 | 2019-08-03 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1126/2018 | 2018-10-29 | 2019-08-01 | MCJ | 6 | 7.1 |  |  | NO |  | Others
MCJ/BU/1160/2018 | 2018-11-07 | 2019-08-23 | MCJ | 6 | 7.1 |  |  | NO |  | Others
MCJ/BU/1132/2018 | 2018-09-26 | 2020-02-11 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1128/2018 | 2018-09-05 | 2019-06-08 | MCJ | 5 | 7.1 |  |  | NO |  | Others
PA/DEP/1135/2018 | 2018-09-10 | 2019-05-08 | PA | 5 | 7 |  |  | NO |  | Others
IM/DEP/1106/2018 | 2018-06-20 | 2019-02-24 | IM | 3 | 6 |  |  | NO |  | Others
PA/DEP/1138/2018 | 2018-09-10 | 2019-05-02 | PA | 5 | 7 |  |  | NO |  | Others
AGGLO/BU/1086/2018 | 2018-06-25 | 2019-04-25 | AGGLO | 3 | 6 |  |  | Yes('01-APR-2019') |  | Others
FAM/BU/1098/2018 | 2019-01-29 | 2019-11-17 | FAM | 3 | 6 |  |  | NO |  | Others
SMC/BU/1119/2018 | 2018-07-30 | 2019-04-28 | SMC | 7 | 7.3 |  |  | NO |  | Others
MCJ/BU/1163/2018 | 2018-10-11 | 2019-06-03 | MCJ | 5 | 7 |  |  | NO |  | Others
PA/DEP/1184/2018 | 2019-01-10 | 2019-06-20 | PA | 5 | 7.1 |  |  | NO |  | Others
PA/DEP/1136/2018 | 2018-10-03 | 2019-05-31 | PA | 5 | 7 |  |  | NO |  | Others
FAM/BU/1099/2018 | 2018-06-22 | 2019-07-14 | FAM | 3 | 5 |  |  | NO |  | Others
RM/BU/1112/2018 | 2018-07-23 | 2019-04-04 | RM | 4 | 7.1 |  |  | NO |  | Others
ENV/BU/1096/2018 | 2018-06-20 | 2019-04-05 | ENV | 6 | 7 | 7.1 | 7.3 | Yes('07-FEB-2019') |  | Others
SMC/BU/1120/2018 | 2018-07-17 | 2019-01-01 | SMC | 7 | 7.3 | 7 | 7.2 | Yes('06-FEB-2019') |  | Others
SMC/BU/1122/2018 | 2018-08-03 | 2019-01-18 | SMC | 7 | 7.2 |  |  | NO |  | Others
ENV/BU/1093/2018 | 2018-07-19 | 2019-05-07 | ENV | 5 | 6 |  |  | NO |  | Others
ENV/BU/1094/2018 | 2018-08-28 | 2019-06-16 | ENV | 6 | 7 |  |  | NO |  | Others
SE/DEP/1178/2018 | 2018-12-24 | 2019-04-14 | SE | 3 | 5 |  |  | NO |  | Others
IM/BU/1107/2018 | 2018-07-02 | 2019-03-08 | IM | 7.1 | 7.3 |  |  | NO |  | Others
ENV/BU/1152/2018 | 2018-12-17 | 2019-08-19 | ENV | 5 | 6 |  |  | NO |  | Others
PA/DEP/1139/2018 | 2018-08-03 | 2019-03-25 | PA | 5 | 7 |  |  | NO |  | Others
PA/DEP/1140/2018 | 2018-09-10 | 2019-05-02 | PA | 3 | 5 |  |  | NO |  | Others
SMC/BU/1123/2018 | 2018-07-06 | 2018-12-21 | SMC | 7 | 7.2 |  |  | NO |  | Others
SE/BU/1179/2018 | 2019-01-18 | 2019-04-27 | SE | 5 | 7.2 |  |  | NO |  | Others
FAM/BU/1100/2018 | 2018-08-06 | 2019-05-30 | FAM | 3 | 6 |  |  | NO |  | Others
IM/BU/1108/2018 | 2018-08-12 | 2019-04-18 | IM | 4 | 6 |  |  | NO |  | Others
ENV/BU/1095/2018 | 2018-07-24 | 2019-04-11 | ENV | 7 | 8 |  |  | NO |  | Others
AGGLO/DEP/1088/2018 | 2018-07-01 | 2019-03-31 | AGGLO | 3 | 5 |  |  | Yes('01-APR-2019') |  | Others
RM/BU/1111/2018 | 2018-07-20 | 2019-04-19 | RM | 4 | 7 |  |  | NO |  | Others
RM/BU/1113/2018 | 2018-08-02 | 2019-04-17 | RM | 5 | 7.1 |  |  | NO |  | Others
FAM/BU/1101/2018 | 2018-06-22 | 2019-04-10 | FAM | 3 | 7.1 |  |  | NO |  | Others
FAM/DEP/1102/2018 | 2018-07-19 | 2019-05-07 | FAM | 2 | 5 |  |  | NO |  | Others
SMC/BU/1173/2018 | 2019-01-31 | 2019-06-14 | SMC | 6 | 7 |  |  | NO |  | Others
PROD/DEP/1144/2018 | 2018-10-03 | 2019-05-10 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others
MWJ/BU/1166/2018 | 2018-10-11 | 2019-04-12 | MWJ | 7 | 7.3 |  |  | NO |  | Others
PROD/DEP/1146/2018 | 2018-10-15 | 2019-05-15 | PROD | 2 | 5 |  |  | NO |  | Others
PROD/BU/1145/2018 | 2018-10-05 | 2019-05-12 | PROD | 3 | 6 |  |  | NO |  | Others
AGGLO/DEP/1154/2018 | 2018-10-15 | 2019-08-14 | AGGLO | 3 | 5 |  |  | NO |  | Others
CCM/BU/1156/2018 | 2018-10-12 | 2019-04-27 | CCM | 4 | 7.1 |  |  | NO |  | Others
PA/DEP/1141/2018 | 2018-10-03 | 2019-04-24 | PA | 5 | 7.1 |  |  | NO |  | Others
SMC/BU/1150/2018 | 2018-10-22 | 2019-07-21 | SMC | 6 | 6 |  |  | NO |  | Others
MWJ/BU/1167/2018 | 2018-10-23 | 2019-05-07 | MWJ | 5 | 7 |  |  | NO |  | Others
SE/TAP/1168/2018 | 2018-10-15 | 2019-10-02 | SE | 6 | 7.3 |  |  | NO |  | Others
SE/DEP/1169/2018 | 2018-12-24 | 2019-12-23 | SE | 3 | 5 |  |  | NO |  | Others
FAM/DEP/1143/2018 | 2018-10-05 | 2019-05-26 | FAM | 2 | 5 |  |  | NO |  | Others
FAM/BU/1157/2018 | 2018-12-03 | 2019-07-19 | FAM | 2 | 6 |  |  | NO |  | Others
CCM/BU/1158/2018 | 2018-09-20 | 2019-09-05 | CCM | 2 | 6 |  |  | NO |  | Others
SMC/BU/1149/2018 | 2018-10-09 | 2019-04-10 | SMC | 7.1 | 7.2 |  |  | NO |  | Others
ENV/BU/1155/2018 | 2018-09-26 | 2019-12-25 | ENV | 7 | 7.3 |  |  | NO |  | Others
PROD/BU/1187/2019 | 2019-02-08 | 2019-05-21 | PROD | 6 | 7 |  |  | NO |  | Others
IM/BU/1147/2018 | 2019-03-20 | 2019-09-01 | IM | 7.3 | 8 |  |  | NO |  | Others
SE/DEP/1174/2018 | 2019-03-04 | 2020-05-23 | SE | 1 | 3 |  |  | NO |  | Others
CCM/DEP/1172/2018 | 2019-01-01 | 2020-01-31 | CCM | 1 | 5 |  |  | NO |  | Others
MC/DEP/1176/2018 | 2018-12-24 | 2019-10-24 | MC | 3 | 5 |  |  | NO |  | Others

## FY-19-Completed
Project Number | Actual SD | Revised ED | Group | TRL From | TRL To | Actual TRL From | Actual TRL To | Completed on | Closed On | Program Area | Avg PPI
PA/TAP/679/2015 | 2015-11-07 | 2018-03-31 | PA | 3 | 6 | 3 | 6 | 2018-05-09 | 2019-02-01 | Others | 96
SMC/ABP/719/2016 | 2016-06-29 | 2018-01-31 | SMC | 7 | 7.3 |  |  | 2018-08-07 | 2019-04-04 | Others | 0
SMC/ABP/730/2016 | 2016-05-30 | 2018-02-28 | SMC | 5 | 7.2 | 5 | 7.2 | 2018-04-23 | 2019-04-04 | Others | 100
MCJ/ABP/767/2016 | 2016-07-29 | 2018-03-30 | MCJ | 5 | 7.1 | 5 | 7.1 | 2018-11-09 | 2019-01-14 | Others | 90
SMC/ABP/751/2016 | 2016-08-18 | 2017-11-30 | SMC | 6 | 7.2 | 6 | 7.2 | 2018-08-02 | 2019-01-14 | Others | 50
SMC/ABP/754/2016 | 2016-07-20 | 2017-03-19 | SMC | 6 | 7.2 | 7.1 | 7.3 | 2018-08-08 | 2019-04-04 | Others | 90
MCJ/DEP/827/2016 | 2016-08-22 | 2018-03-31 | MCJ | 2 | 5 | 1 | 4 | 2018-05-15 | 2018-11-08 | Others | 90
MCJ/ABP/807/2016 | 2016-08-31 | 2018-03-30 | MCJ | 4 | 7 | 2 | 5 | 2018-05-15 | 2018-09-12 | Others | 95
PROD/DEP/822/2016 | 2016-08-22 | 2018-02-06 | PROD | 7.3 | 8 | 7 | 7.3 | 2018-04-29 | 2019-03-06 | Others | 90
IM/DEP/859/2016 | 2016-12-09 | 2018-04-08 | IM | 3 | 6 | 2 | 3 | 2018-07-02 | 2019-03-05 | Others | 95
RM/ABP/784/2016 | 2016-09-02 | 2018-02-28 | RM | 5 | 7.1 | 5 | 8 | 2018-04-23 | 2018-06-21 | Others | 89
SMC/ABP/799/2016 | 2017-02-04 | 2017-09-18 | SMC | 7.1 | 7.2 |  |  | 2018-12-18 | 2019-03-06 | Others | 0
ENV/DEP/819/2016 | 2016-10-06 | 2017-11-06 | ENV | 2 | 5 |  |  | 2018-07-10 | 2018-12-14 | Others | 0
ENV/DEP/833/2016 | 2016-10-06 | 2017-10-05 | ENV | 2 | 5 |  |  | 2018-07-10 | 2018-12-14 | Others | 0
MCJ/DEP/830/2016 | 2016-09-05 | 2017-12-05 | MCJ | 2 | 5 |  |  | 2018-11-09 | 2018-12-12 | Others | 0
SMC/ABP/841/2016 | 2017-01-21 | 2017-07-21 | SMC | 6 | 7.1 |  |  | 2018-04-05 | 2018-06-29 | Others | 0
RM/ABP/853/2016 | 2016-11-28 | 2017-12-31 | RM | 4 | 6 | 5 | 6 | 2018-04-23 | 2018-06-21 | Others | 100
MCJ/DEP/860/2016 | 2016-12-09 | 2018-03-30 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-11-08 | Others | 93
MCJ/ABP/865/2016 | 2017-01-03 | 2018-03-31 | MCJ | 5 | 7.1 | 1 | 7.2 | 2018-05-15 | 2018-11-08 | Others | 100
MMPD/DEP/1007/2018 | 2018-01-29 | 2018-11-30 | MMPD | 3 | 6 | 6 | 7 | 2018-12-06 | 2019-01-30 | Others | 95
MMPD/ABP/861/2016 | 2017-02-15 | 2018-01-31 | MMPD | 6 | 7.1 | 7.1 | 8 | 2018-04-29 | 2019-03-06 | Others | 90
SMC/ABP/858/2016 | 2017-03-01 | 2017-07-30 | SMC | 7 | 7.2 | 7 | 7.1 | 2018-08-07 | 2019-01-31 | Others | 91
MCJ/ABP/864/2016 | 2017-01-30 | 2018-02-28 | MCJ | 6 | 7.1 | 6 | 7.1 | 2018-04-04 | 2018-11-08 | Others | 95
ENV/DEP/879/2017 | 2017-09-05 | 2018-07-24 | ENV | 3 | 4 |  |  | 2018-07-29 | 2018-12-14 | Others | 0
IM/BU/888/2017 | 2017-08-24 | 2018-02-11 | IM | 6 | 7 | 6 | 7 | 2018-10-29 | 2018-11-29 | Others | 95
PROD/DEP/872/2017 | 2017-08-21 | 2018-05-17 | PROD | 3 | 5 |  |  | 2018-08-31 | 2019-03-06 | Others | 0
IM/BU/878/2017 | 2017-08-24 | 2018-05-19 | IM | 7 | 8 | 7 | 7.1 | 2018-10-22 | 2018-12-14 | Others | 95
IM/BU/889/2017 | 2017-08-24 | 2018-05-27 | IM | 7 | 8 | 7 | 7.2 | 2018-11-12 | 2018-11-29 | Others | 100
PROD/DEP/873/2017 | 2017-08-21 | 2018-04-26 | PROD | 3 | 6 | 6 | 7.1 | 2018-05-16 | 2019-03-06 | Others | 90
FAM/BU/893/2017 | 2017-08-09 | 2018-05-27 | FAM | 2 | 8 | 2 | 8 | 2018-06-22 | 2018-08-01 | Others | 90
PROD/DEP/965/2017 | 2017-08-21 | 2018-05-17 | PROD | 5 | 6 | 5 | 6 | 2018-05-16 | 2019-03-06 | Others | 100
PROD/BU/905/2017 | 2017-09-21 | 2018-06-17 | PROD | 3 | 7 |  |  | 2018-08-31 | 2019-03-06 | Others | 0
PROD/BU/927/2017 | 2017-09-19 | 2018-06-15 | PROD | 5 | 6 | 5 | 6 | 2018-05-08 | 2019-03-06 | Others | 95
FAM/DEP/899/2017 | 2017-08-31 | 2018-06-18 | FAM | 2 | 6 | 2 | 6 | 2018-07-06 | 2018-08-01 | Others | 85
IM/BU/900/2017 | 2017-08-24 | 2018-05-20 | IM | 3 | 6 | 3 | 7 | 2018-06-12 | 2018-11-29 | Others | 100
PROD/BU/907/2017 | 2017-08-21 | 2018-05-17 | PROD | 6 | 7.3 |  |  | 2018-05-16 | 2019-03-06 | Others | 0
PROD/DEP/908/2017 | 2017-08-21 | 2018-05-17 | PROD | 5 | 6 | 5 | 6 | 2018-05-16 | 2019-03-06 | Others | 90
MCJ/BU/943/2017 | 2017-08-22 | 2018-05-30 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-06-01 | Others | 96
PROD/BU/909/2017 | 2017-08-23 | 2018-09-30 | PROD | 7.1 | 8 | 7.1 | 8 | 2018-10-05 | 2019-03-06 | Others | 90
MCJ/BU/944/2017 | 2017-09-01 | 2018-05-06 | MCJ | 7.3 | 8 | 7.3 | 7.3 | 2018-05-15 | 2018-11-08 | Others | 91
PROD/BU/911/2017 | 2017-11-01 | 2018-07-28 | PROD | 3 | 7.3 | 7.3 | 7.3 | 2018-04-29 | 2019-02-20 | Others | 95
MCJ/BU/945/2017 | 2017-08-09 | 2018-05-04 | MCJ | 5 | 7.1 | 5 | 6 | 2018-05-15 | 2018-11-08 | Others | 91
SMC/BU/901/2017 | 2017-08-31 | 2018-04-16 | SMC | 7 | 7.3 | 7 | 7 | 2018-04-27 | 2019-04-01 | Others | 75
FAM/DEP/918/2017 | 2017-08-18 | 2018-05-08 | FAM | 3 | 5 | 3 | 5 | 2018-07-09 | 2018-08-01 | Others | 85
SE/TAP/916/2017 | 2017-09-05 | 2018-06-05 | SE | 4 | 5 | 4 | 6 | 2018-04-13 | 2019-02-13 | Others | 97
CCM/BU/919/2017 | 2017-09-20 | 2018-12-20 | CCM | 3 | 7.1 | 3 | 7 | 2019-01-28 | 2019-02-18 | Others | 92
CCM/DEP/921/2017 | 2017-08-21 | 2018-11-21 | CCM | 1 | 5 | 1 | 5 | 2018-11-22 | 2019-02-18 | Others | 90
SMC/BU/974/2017 | 2017-10-31 | 2018-05-15 | SMC | 7 | 7.3 | 7 | 7.3 | 2018-04-13 | 2019-01-14 | Others | 100
SMC/BU/923/2017 | 2017-08-31 | 2018-03-30 | SMC | 7 | 7.2 | 7 | 7.2 | 2018-06-26 | 2018-07-25 | Others | 97
FAM/BU/926/2017 | 2017-08-30 | 2018-06-10 | FAM | 3 | 7.1 | 3 | 7.1 | 2019-02-19 | 2019-04-05 | Others | 95
RM/BU/977/2017 | 2017-10-09 | 2018-06-05 | RM | 6 | 7.1 | 7.1 | 8 | 2018-12-27 | 2019-01-04 | Others | 97
SE/BU/939/2017 | 2017-10-04 | 2018-07-04 | SE | 7.1 | 7.3 | 7.1 | 7.2 | 2018-07-24 | 2019-03-06 | Others | 95
SE/BU/998/2017 | 2017-11-09 | 2018-05-25 | SE | 3 | 7.1 | 3 | 7.2 | 2018-04-13 | 2018-06-29 | Others | 90
NDTS/DEP/966/2017 | 2017-08-28 | 2018-10-31 | NDTS | 2 | 5 | 2 | 5 | 2018-11-07 | 2019-02-21 | Others | 100
MCJ/BU/986/2017 | 2017-12-22 | 2018-08-01 | MCJ | 7.1 | 7.3 | 7.1 | 7.2 | 2018-09-12 | 2018-11-08 | Others | 90
MCJ/BU/950/2017 | 2017-11-09 | 2018-07-26 | MCJ | 3 | 6 | 3 | 6 | 2018-05-15 | 2018-11-08 | Others | 92
MCJ/BU/952/2017 | 2017-09-01 | 2018-05-08 | MCJ | 6 | 7.2 | 6 | 7.2 | 2018-05-15 | 2018-11-08 | Others | 96
MCJ/DEP/951/2017 | 2017-08-31 | 2018-04-21 | MCJ | 5 | 7 | 5 | 7 | 2018-05-15 | 2018-11-08 | Others | 100
PROD/DEP/978/2017 | 2017-09-21 | 2018-05-21 | PROD | 2 | 6 | 2 | 6 | 2018-05-16 | 2019-03-06 | Others | 100
SMC/BU/980/2017 | 2017-10-13 | 2018-04-27 | SMC | 7 | 7.3 | 7 | 7.3 | 2018-04-04 | 2018-05-02 | Others | 98
CCM/BU/961/2017 | 2017-08-24 | 2018-05-08 | CCM | 4 | 8 | 4 | 8 | 2018-06-21 | 2018-11-29 | Others | 75
CCM/TAP/959/2017 | 2017-08-09 | 2018-04-08 | CCM | 3 | 5 | 3 | 4 | 2018-04-03 | 2019-03-22 | Others | 95
SMC/BU/981/2017 | 2017-11-02 | 2018-04-19 | SMC | 7 | 7.3 | 6 | 7.3 | 2018-05-17 | 2018-06-29 | Others | 100
SE/TAP/990/2017 | 2017-11-02 | 2018-11-30 | SE | 7.1 | 7.3 | 7.1 | 7.3 | 2018-11-28 | 2019-02-12 | Others | 98
SMC/BU/995/2017 | 2017-10-16 | 2018-03-31 | SMC | 7 | 7.2 | 6 | 7.1 | 2018-04-27 | 2018-06-08 | Others | 5
PROD/BU/984/2017 | 2017-10-11 | 2018-04-19 | PROD | 5 | 8 | 6 | 7 | 2018-04-29 | 2019-03-06 | Others | 90
SE/TAP/991/2017 | 2017-11-02 | 2018-10-31 | SE | 4 | 5 | 4 | 5 | 2019-01-10 | 2019-02-12 | Others | 96
SE/BU/989/2017 | 2017-11-02 | 2018-05-02 | SE | 8 | 8 | 8 | 8 | 2018-05-14 | 2018-06-29 | Others | 95
MCJ/DEP/1001/2017 | 2018-01-19 | 2018-06-18 | MCJ | 5 | 7.1 | 3 | 4 | 2018-08-03 | 2018-11-08 | Others | 85
NDTS/BU/993/2017 | 2017-10-06 | 2018-04-05 | NDTS | 7.1 | 7.2 | 7.1 | 7.2 | 2018-05-11 | 2018-08-07 | Others | 100
PROD/BU/1006/2018 | 2018-02-20 | 2019-01-31 | PROD | 6 | 7 | 7 | 7.3 | 2019-02-11 | 2019-04-01 | Others | 100
PROD/DEP/1003/2017 | 2018-01-10 | 2018-08-02 | PROD | 1 | 6 | 1 | 5 | 2018-07-05 | 2019-03-06 | Others | 100
SMC/BU/1010/2018 | 2018-03-03 | 2018-05-03 | SMC | 7.1 | 7.2 | 7.1 | 7.2 | 2018-04-05 | 2018-06-08 | Others | 70
SMC/BU/1011/2018 | 2018-04-24 | 2018-07-27 | SMC | 7 | 7.2 | 7 | 7.2 | 2018-08-02 | 2018-11-28 | Others | 100
IM/BU/1059/2018 | 2018-05-02 | 2019-02-28 | IM | 4 | 7.1 | 4 | 8 | 2019-03-20 | 2019-03-22 | Others | 90
SE/BU/1065/2018 | 2018-05-21 | 2019-03-28 | SE | 2 | 5 | 2 | 8 | 2019-02-26 | 2019-04-04 | Others | 95
SE/BU/1014/2018 | 2018-06-11 | 2019-04-18 | SE | 2 | 7 | 2 | 6 | 2019-02-26 | 2019-04-04 | Others | 97
AGGLO/TAP/1031/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 90
AGGLO/TAP/1045/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 100
AGGLO/DEP/1053/2018 | 2018-06-04 | 2019-02-18 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-18 | 2019-02-19 | Others | 95
IM/BU/1061/2018 | 2018-06-07 | 2019-03-23 | IM | 7 | 8 | 4 | 7 | 2019-03-19 | 2019-03-20 | Others | 100
AGGLO/DEP/1057/2018 | 2018-05-30 | 2019-02-13 | AGGLO | 2 | 3 | 2 | 3 | 2019-02-13 | 2019-02-18 | Others | 95
IM/BU/1060/2018 | 2018-05-02 | 2019-02-15 | IM | 4 | 6 | 4 | 6 | 2019-03-19 | 2019-03-20 | Others | 97
ENV/BU/1092/2018 | 2018-07-24 | 2019-02-11 | ENV | 7 | 8 | 4 | 7 | 2019-02-10 | 2019-02-12 | Others | 95
AGGLO/TAP/1087/2018 | 2018-06-20 | 2019-04-05 | AGGLO | 3 | 5 | 3 | 5 | 2019-02-15 | 2019-02-18 | Others | 100
ENV/TAP/1148/2018 | 2018-12-07 | 2020-06-08 | ENV | 6 | 7 | 4 | 7.1 | 2019-02-12 | 2019-02-15 | Others | 100
IFA/ABP/517/2014 | 2014-08-01 | 2016-03-31 | FAM | 1 | 5 |  |  | 2018-08-13 | 2018-09-07 | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS | 0
IFA/TAP/520/2014 | 2014-08-05 | 2016-03-31 | FAM | 6 | 7.2 |  |  | 2018-07-30 | 2018-09-07 | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS | 0
PROD/DEP/573/2015 | 2015-06-20 | 2016-03-20 | PROD | 3 | 5 |  |  | 2018-08-01 | 2019-03-06 | AUTOMOTIVE | 0
SMC/ABP/637/2015 | 2015-09-02 | 2016-04-02 | SMC | 6 | 7 | 6 | 7 | 2018-04-04 | 2018-07-02 | STEELMAKING AND CASTING | 90
PROD/ABP/661/2015 | 2015-12-11 | 2017-11-30 | PROD | 2 | 5 | 2 | 5 | 2018-06-18 | 2019-03-06 | Others | 90
SMC/DEP/677/2015 | 2015-11-24 | 2016-10-31 | SMC | 5 | 5 |  |  | Yes('18-DEC-2018') |  | Others
PA/DEP/681/2015 | 2015-12-19 | 2018-06-30 | PA | 5 | 7.1 | 1 | 3 | Yes('09-MAY-2018') |  | Others
PA/TAP/680/2015 | 2015-12-19 | 2018-04-30 | PA | 3 | 7.1 | 1 | 6 | Yes('09-JUL-2018') |  | Others
RM/ABP/673/2015 | 2016-02-03 | 2016-09-02 | RM | 4 | 6 |  |  | Yes('07-JAN-2019') |  | Others
ENV/ABP/691/2015 | 2016-01-05 | 2019-03-31 | ENV | 6 | 7 |  |  | Yes('18-MAR-2019') |  | Others
PA/DEP/726/2016 | 2016-06-27 | 2017-08-11 | PA | 3 | 5 |  |  | Yes('09-MAY-2018') |  | Others
ENV/TAP/729/2016 | 2016-09-20 | 2018-09-19 | ENV | 3 | 7 |  |  | Yes('20-SEP-2018') |  | Others
AGGLO/ABP/791/2016 | 2016-09-06 | 2017-09-05 | AGGLO | 3 | 6 |  |  | Yes('21-AUG-2018') |  | Others
MCJ/ABP/772/2016 | 2016-07-22 | 2018-01-31 | MCJ | 5 | 7.1 |  |  | Yes('15-MAY-2018') |  | Others
PA/DEP/763/2016 | 2016-07-18 | 2018-03-23 | PA | 4 | 6 |  |  | Yes('09-MAY-2018') |  | Others
SMC/ABP/749/2016 | 2017-08-02 | 2018-05-18 | SMC | 6 | 7.1 |  |  | Yes('18-DEC-2018') |  | Others
PROD/ABP/762/2016 | 2016-07-19 | 2017-07-31 | PROD | 6 | 7.1 | 6 | 7.1 | Yes('29-APR-2018') |  | Others
SMC/ABP/753/2016 | 2016-11-24 | 2017-08-08 | SMC | 7 | 7.3 |  |  | Yes('18-DEC-2018') |  | Others
PA/ABP/803/2016 | 2016-09-30 | 2017-12-07 | PA | 7 | 8 | 7 | 8 | Yes('09-MAY-2018') |  | Others
PA/DEP/825/2016 | 2016-09-05 | 2018-03-31 | PA | 3 | 7 | 6 | 7.1 | Yes('09-MAY-2018') |  | Others
PA/ABP/804/2016 | 2016-09-27 | 2018-03-31 | PA | 5 | 7.3 | 5 | 7.3 | Yes('09-MAY-2018') |  | Others
NDTS/DEP/832/2016 | 2016-09-05 | 2018-01-31 | NDTS | 2 | 7.1 | 6 | 7.2 | Yes('09-OCT-2018') |  | Others
PROD/ABP/851/2016 | 2016-11-03 | 2019-02-28 | PROD | 5 | 6 |  |  | Yes('01-MAR-2019') |  | Others
ENV/ABP/863/2016 | 2016-12-06 | 2018-03-31 | ENV | 5 | 6 |  |  | Yes('29-APR-2018') |  | Others
PA/ABP/868/2016 | 2017-02-14 | 2017-12-31 | PA | 5 | 7 |  |  | Yes('13-FEB-2019') |  | Others
ENV/ABP/870/2017 | 2017-03-14 | 2019-03-31 | ENV | 5 | 6 |  |  | Yes('03-NOV-2018') |  | Others
ENV/TAP/871/2017 | 2017-05-10 | 2018-06-06 | ENV | 5 | 7 |  |  | Yes('09-JUL-2018') |  | Others
PROD/BU/967/2017 | 2017-10-09 | 2018-07-05 | PROD | 6 | 8 | 5 | 7 | Yes('06-DEC-2018') |  | Others
ENV/BU/881/2017 | 2017-08-09 | 2018-06-27 | ENV | 7.1 | 8 |  |  | Yes('29-APR-2018') |  | Others
SE/BU/997/2017 | 2018-07-24 | 2019-02-06 | SE | 7.1 | 7.3 |  |  | Yes('26-FEB-2019') |  | Others
PROD/DEP/875/2017 | 2017-10-05 | 2019-02-04 | PROD | 5 | 6 | 5 | 6 | Yes('11-FEB-2019') |  | Others
RM/BU/896/2017 | 2017-09-06 | 2018-06-22 | RM | 3 | 6 |  |  | Yes('11-OCT-2018') |  | Others
RM/TAP/885/2017 | 2017-08-09 | 2018-05-25 | RM | 1 | 3 | 5 | 6 | Yes('28-NOV-2018') |  | Others
RM/TAP/897/2017 | 2017-08-21 | 2018-06-06 | RM | 3 | 5 |  |  | Yes('08-JAN-2019') |  | Others
PA/DEP/955/2017 | 2017-09-21 | 2018-06-24 | PA | 3 | 5 | 3 | 5 | Yes('09-MAY-2018') |  | Others
MCJ/BU/964/2017 | 2017-08-17 | 2018-11-30 | MCJ | 7.1 | 8 | 7.1 | 8 | Yes('11-DEC-2018') |  | Others
SE/DEP/914/2017 | 2017-09-05 | 2018-06-05 | SE | 2 | 5 | 2 | 5 | Yes('25-JUN-2018') |  | Others
PA/BU/956/2017 | 2017-11-14 | 2018-08-17 | PA | 6 | 7.3 | 6 | 7.3 | Yes('09-MAY-2018') |  | Others
PROD/BU/910/2017 | 2017-08-31 | 2018-11-30 | PROD | 5 | 6 | 6 | 7.3 | Yes('06-DEC-2018') |  | Others
PROD/DEP/912/2017 | 2017-08-21 | 2018-11-16 | PROD | 3 | 6 | 4 | 6 | Yes('06-DEC-2018') |  | Others
MCJ/BU/946/2017 | 2017-08-09 | 2018-04-30 | MCJ | 6 | 7.2 |  |  | Yes('09-NOV-2018') |  | Others
SE/DEP/915/2017 | 2017-09-05 | 2018-05-27 | SE | 3 | 5 | 3 | 6 | Yes('13-APR-2018') |  | Others
SE/DEP/970/2017 | 2017-08-31 | 2018-05-31 | SE | 3 | 5 |  |  | Yes('13-APR-2018') |  | Others
SE/DEP/936/2017 | 2017-08-21 | 2018-10-31 | SE | 3 | 5 |  |  | Yes('09-NOV-2018') |  | Others
RM/DEP/904/2017 | 2017-09-21 | 2018-07-07 | RM | 3 | 5 |  |  | Yes('10-AUG-2018') |  | Others
CCM/DEP/922/2017 | 2017-09-21 | 2018-09-20 | CCM | 1 | 5 |  |  | Yes('03-APR-2018') |  | Others
PA/BU/969/2017 | 2017-09-19 | 2018-06-22 | PA | 6 | 8 | 6 | 8 | Yes('09-MAY-2018') |  | Others
SMC/DEP/934/2017 | 2018-01-12 | 2018-09-11 | SMC | 6 | 6 |  |  | Yes('15-OCT-2018') |  | Others
SE/DEP/937/2017 | 2017-08-31 | 2018-12-31 | SE | 2 | 5 |  |  | Yes('10-JAN-2019') |  | Others
NDTS/BU/941/2017 | 2017-08-04 | 2018-06-30 | NDTS | 3 | 7 | 7 | 7.3 | Yes('29-JUN-2018') |  | Others
PROD/DEP/913/2017 | 2017-08-18 | 2018-05-13 | PROD | 3 | 6 | 5 | 6 | Yes('16-MAY-2018') |  | Others
SE/BU/938/2017 | 2017-09-06 | 2018-10-08 | SE | 3 | 7.1 |  |  | Yes('28-NOV-2018') |  | Others
SE/BU/940/2017 | 2017-08-23 | 2018-05-07 | SE | 3 | 7.1 | 3 | 4 | Yes('28-MAY-2018') |  | Others
CCM/DEP/960/2017 | 2017-08-16 | 2018-08-15 | CCM | 1 | 5 |  |  | Yes('20-AUG-2018') |  | Others
SMC/BU/962/2017 | 2018-05-28 | 2019-01-25 | SMC | 6 | 6 |  |  | Yes('06-MAR-2019') |  | Others
PROD/DEP/979/2017 | 2017-11-02 | 2018-12-31 | PROD | 2 | 5 | 6 | 8 | Yes('11-FEB-2019') |  | Others
PROD/DEP/983/2017 | 2017-11-02 | 2019-01-31 | PROD | 2 | 6 | 2 | 6 | Yes('11-FEB-2019') |  | Others
SMC/BU/996/2017 | 2017-10-16 | 2018-03-31 | SMC | 7 | 7.2 | 7 | 7.2 | Yes('15-MAR-2019') |  | Others
SE/BU/999/2017 | 2018-02-20 | 2019-03-15 | SE | 7.1 | 8 |  |  | Yes('21-MAR-2019') |  | Others
SE/DEP/988/2017 | 2017-11-02 | 2018-05-18 | SE | 5 | 6 | 5 | 5 | Yes('13-APR-2018') |  | Others
NDTS/DEP/1071/2018 | 2018-06-04 | 2019-04-05 | NDTS | 3 | 7.1 | 3 | 7.2 | Yes('22-FEB-2019') |  | Others
ENV/DEP/1024/2018 | 2018-05-23 | 2019-05-18 | ENV | 4 | 6 |  |  | Yes('27-MAR-2019') |  | Others
ENV/DEP/1027/2018 | 2018-05-30 | 2019-05-20 | ENV | 3 | 5 |  |  | Yes('25-MAR-2019') |  | Others
IM/BU/1104/2018 | 2018-09-11 | 2019-05-18 | IM | 7.1 | 7.3 |  |  | Yes('21-MAR-2019') |  | Others
SMC/BU/1114/2018 | 2018-06-27 | 2019-03-28 | SMC | 7.1 | 7.3 |  |  | Yes('04-MAR-2019') |  | Others
SMC/DEP/1142/2018 | 2018-10-31 | 2019-04-17 | SMC | 6 | 6 |  |  | Yes('28-MAR-2019') |  | Others
SE/BU/1067/2018 | 2018-05-21 | 2019-03-19 | SE | 2 | 6 | 2 | 6 | Yes('26-FEB-2019') |  | Others
SMC/BU/1118/2018 | 2018-07-06 | 2019-02-21 | SMC | 7 | 7.3 |  |  | Yes('06-MAR-2019') |  | Others
PROD/DEP/1074/2018 | 2018-05-30 | 2019-03-28 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others
ENV/BU/1096/2018 | 2018-06-20 | 2019-04-05 | ENV | 6 | 7 | 7.1 | 7.3 | Yes('07-FEB-2019') |  | Others
SMC/BU/1120/2018 | 2018-07-17 | 2019-01-01 | SMC | 7 | 7.3 | 7 | 7.2 | Yes('06-FEB-2019') |  | Others
PROD/DEP/1144/2018 | 2018-10-03 | 2019-05-10 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others
RC/ABP/458/2014 | 2014-09-12 | 2015-03-14 | RM | 2 | 5 |  |  | Yes('04-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
RC/DEP/466/2014 | 2014-07-31 | 2016-07-31 | RM | 3 | 6 |  |  | Yes('04-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
RC/ABP/529/2014 | 2014-10-28 | 2016-03-31 | RM | 4 | 5 |  |  | Yes('21-JUN-2018') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
CCM/TAP/557/2015 | 2015-04-10 | 2017-12-31 | CCM | 1 | 7.1 |  |  | Yes('05-NOV-2018') |  | AGGLOMERATION AND IRON MAKING
RM/TAP/652/2015 | 2015-11-10 | 2017-03-31 | RM | 1 | 4 |  |  | Yes('27-DEC-2018') |  | Others
MCJ/TAP/609/2015 | 2015-07-22 | 2017-04-21 | RM | 3 | 4 |  |  | Yes('16-JAN-2019') |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS
SMC/ABP/615/2015 | 2015-09-19 | 2016-03-06 | SMC | 6 | 7 |  |  | Yes('14-DEC-2018') |  | STEELMAKING AND CASTING

## Rolling-To-Next-FY
Project Number | Actual SD | Revised ED | Group | TRL From | TRL To | Actual TRL From | Actual TRL To | Completed on | Closed On | Program Area | Avg PPI
IM/ABP/794/2016 | 2016-08-17 | 2019-04-15 | IM | 3 | 7 | 3 | 7.1 | 2019-04-04 | 2019-04-09 | Others | 97
IM/ABP/739/2016 | 2016-08-02 | 2019-03-15 | IM | 3 | 4 |  |  | Yes('04-APR-2019') |  | Others
NDTS/DEP/834/2016 | 2016-10-07 | 2018-12-31 | NDTS | 2 | 7.1 |  |  | NO |  | Others
IM/DEP/740/2016 | 2016-07-28 | 2019-02-28 | IM | 3 | 5 |  |  | NO |  | Others
MMPD/ABP/844/2016 | 2017-04-21 | 2017-11-10 | MMPD | 2 | 7.1 |  |  | NO |  | Others
FAM/BU/973/2017 | 2017-09-18 | 2018-12-31 | FAM | 3 | 5 |  |  | NO |  | Others
PA/DEP/954/2017 | 2017-08-21 | 2019-02-28 | PA | 3 | 6 |  |  | NO |  | Others
FAM/DEP/886/2017 | 2017-08-25 | 2018-12-15 | FAM | 3 | 7.2 |  |  | NO |  | Others
ENV/BU/877/2017 | 2017-09-18 | 2019-08-18 | ENV | 4 | 6 |  |  | NO |  | Others
ENV/TAP/883/2017 | 2017-09-04 | 2019-02-28 | ENV | 3 | 4 |  |  | NO |  | Others
IM/DEP/892/2017 | 2017-08-09 | 2019-02-28 | IM | 3 | 5 |  |  | NO |  | Others
NDTS/BU/1005/2018 | 2018-02-07 | 2019-05-31 | NDTS | 7 | 8 |  |  | NO |  | Others
PROD/BU/906/2017 | 2017-08-23 | 2018-11-30 | PROD | 7.1 | 7.3 |  |  | NO |  | Others
RM/TAP/894/2017 | 2017-08-31 | 2019-03-18 | RM | 7.1 | 7.3 |  |  | NO |  | Others
RM/TAP/880/2017 | 2017-08-09 | 2020-01-31 | RM | 3 | 7.1 |  |  | NO |  | Others
IM/DEP/895/2017 | 2017-08-21 | 2019-02-15 | IM | 3 | 5 |  |  | NO |  | Others
ENV/TAP/903/2017 | 2017-08-31 | 2019-05-31 | ENV | 3 | 4 |  |  | NO |  | Others
MCJ/BU/947/2017 | 2017-10-23 | 2018-06-28 | MCJ | 6 | 7.1 |  |  | NO |  | Others
NDTS/BU/1000/2017 | 2018-10-10 | 2019-07-10 | NDTS | 6 | 7.3 |  |  | NO |  | Others
RM/BU/925/2017 | 2017-08-10 | 2018-05-10 | RM | 3 | 6 |  |  | NO |  | Others
CCM/BU/930/2017 | 2017-08-31 | 2018-06-16 | CCM | 3 | 7.1 |  |  | NO |  | Others
ENV/BU/972/2017 | 2017-10-01 | 2018-12-31 | ENV | 7.1 | 7.3 |  |  | NO |  | Others
NDTS/DEP/942/2017 | 2018-07-11 | 2019-07-07 | NDTS | 1 | 6 |  |  | NO |  | Others
MCJ/BU/987/2017 | 2017-11-10 | 2019-03-31 | MCJ | 5 | 7 |  |  | NO |  | Others
PA/DEP/874/2017 | 2017-08-21 | 2019-02-28 | PA | 3 | 6 |  |  | NO |  | Others
FAM/TAP/935/2017 | 2017-08-30 | 2018-05-14 | FAM | 7 | 7 |  |  | NO |  | Others
MCJ/BU/968/2017 | 2017-09-01 | 2018-12-31 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/953/2017 | 2017-09-01 | 2019-02-28 | MCJ | 5 | 7.1 |  |  | NO |  | Others
SE/BU/992/2017 | 2017-12-06 | 2019-03-30 | SE | 5 | 7.1 |  |  | NO |  | Others
FAM/BU/958/2017 | 2017-09-01 | 2019-05-16 | FAM | 3 | 6 |  |  | NO |  | Others
RC-PCAC/DEP/1002/2017 | 2018-01-10 | 2018-07-10 | RC-PCAC | 3 | 5 |  |  | NO |  | Others
PROD/BU/1068/2018 | 2018-06-11 | 2018-12-11 | PROD | 6 | 8 |  |  | NO |  | Others
MCJ/BU/1004/2017 | 2018-02-28 | 2019-02-28 | MCJ | 5 | 7 |  |  | NO |  | Others
FAM/BU/1012/2018 | 2018-04-24 | 2018-12-24 | FAM | 3 | 6 |  |  | NO |  | Others
NDTS/BU/1072/2018 | 2018-06-04 | 2019-02-28 | NDTS | 3 | 7 |  |  | NO |  | Others
SMC/DEP/1013/2018 | 2018-05-11 | 2019-02-28 | SMC | 7 | 7.2 |  |  | Yes('04-APR-2019') |  | Others
PROD/BU/1008/2018 | 2018-02-19 | 2018-06-18 | PROD | 6 | 7.3 |  |  | NO |  | MILLS PROCESSES
ENV/TAP/1022/2018 | 2018-05-30 | 2019-05-25 | ENV | 7 | 8 |  |  | NO |  | Others
PROD/BU/1073/2018 | 2018-05-15 | 2019-03-14 | PROD | 3 | 7.3 |  |  | NO |  | Others
PROD/BU/1171/2018 | 2018-10-11 | 2019-06-09 | PROD | 3 | 6 |  |  | NO |  | Others
MCJ/BU/1127/2018 | 2018-11-08 | 2019-08-11 | MCJ | 6 | 7.1 |  |  | NO |  | Others
PROD/DEP/1082/2018 | 2018-09-21 | 2019-07-20 | PROD | 5 | 7 |  |  | NO |  | Others
ENV/DEP/1023/2018 | 2018-05-11 | 2019-05-06 | ENV | 5 | 7 |  |  | NO |  | Others
ENV/BU/1159/2018 | 2018-10-08 | 2019-05-07 | ENV | 6 | 7 |  |  | NO |  | Others
ENV/DEP/1026/2018 | 2018-05-30 | 2019-05-20 | ENV | 3 | 5 |  |  | NO |  | Others
ENV/DEP/1019/2018 | 2018-06-18 | 2019-06-08 | ENV | 6 | 7 |  |  | NO |  | Others
ENV/BU/1029/2018 | 2018-06-04 | 2019-05-26 | ENV | 5 | 6 |  |  | NO |  | Others
RM/BU/1030/2018 | 2018-07-02 | 2019-04-18 | RM | 5 | 7.1 |  |  | NO |  | Others
SMC/BU/1121/2018 | 2018-07-06 | 2019-03-24 | SMC | 6 | 7.3 |  |  | Yes('03-APR-2019') |  | Others
AGGLO/TAP/1033/2018 | 2018-05-30 | 2019-03-16 | AGGLO | 5 | 7.1 |  |  | NO |  | Others
ENV/BU/1034/2018 | 2018-08-03 | 2019-07-29 | ENV | 6 | 7 |  |  | NO |  | Others
IM/BU/1103/2018 | 2018-08-03 | 2019-05-09 | IM | 7 | 7.2 |  |  | NO |  | Others
RM/BU/1125/2018 | 2018-08-10 | 2020-02-24 | RM | 4 | 5 |  |  | NO |  | Others
CCM/DEP/1035/2018 | 2018-05-11 | 2019-03-21 | CCM | 1 | 4 |  |  | NO |  | Others
RM/DEP/1036/2018 | 2018-06-05 | 2019-03-06 | RM | 3 | 4 |  |  | NO |  | Others
CCM/TAP/1037/2018 | 2018-04-25 | 2019-03-05 | CCM | 4 | 6 |  |  | NO |  | Others
CCM/TAP/1038/2018 | 2018-05-11 | 2019-03-26 | CCM | 4 | 6 |  |  | NO |  | Others
CCM/BU/1040/2018 | 2018-04-19 | 2019-03-04 | CCM | 5 | 7.1 |  |  | NO |  | Others
RM/BU/1109/2018 | 2018-07-25 | 2020-01-24 | RM | 3 | 7 |  |  | NO |  | Others
FAM/BU/1041/2018 | 2018-06-19 | 2019-07-09 | FAM | 3 | 6 |  |  | NO |  | Others
RM/DEP/1042/2018 | 2018-05-30 | 2019-04-28 | RM | 3 | 4 |  |  | NO |  | Others
RM/DEP/1044/2018 | 2018-06-28 | 2019-03-27 | RM | 3 | 4 |  |  | NO |  | Others
CCM/DEP/1020/2018 | 2018-05-11 | 2019-03-26 | CCM | 3 | 5 |  |  | NO |  | Others
SE/DEP/1063/2018 | 2018-09-10 | 2020-05-10 | SE | 4 | 7.3 |  |  | NO |  | Others
RM/TAP/1055/2018 | 2018-09-10 | 2019-07-10 | RM | 4 | 6 |  |  | NO |  | Others
CCM/DEP/1047/2018 | 2018-04-25 | 2019-03-10 | CCM | 1 | 5 |  |  | NO |  | Others
RM/TAP/1048/2018 | 2018-06-18 | 2019-05-02 | RM | 6 | 7 |  |  | NO |  | Others
AGGLO/BU/1049/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 3 | 6 |  |  | Yes('01-APR-2019') |  | Others
AGGLO/DEP/1052/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 |  |  | NO |  | Others
RM/BU/1110/2018 | 2018-07-27 | 2019-04-27 | RM | 5 | 7.2 |  |  | NO |  | Others
RM/TAP/1051/2018 | 2018-05-30 | 2019-04-18 | RM | 3 | 4 |  |  | NO |  | Others
AGGLO/BU/1084/2018 | 2018-07-04 | 2019-03-05 | AGGLO | 4 | 6 |  |  | NO |  | Others
AGGLO/DEP/1054/2018 | 2018-06-06 | 2019-04-20 | AGGLO | 3 | 6 |  |  | NO |  | Others
PROD/DEP/1079/2018 | 2018-12-24 | 2019-10-23 | PROD | 3 | 6 |  |  | NO |  | Others
PROD/DEP/1064/2018 | 2018-06-28 | 2019-04-27 | PROD | 2 | 6 |  |  | Yes('01-APR-2019') |  | Others
AGGLO/DEP/1085/2018 | 2018-06-28 | 2019-05-14 | AGGLO | 3 | 5 |  |  | NO |  | Others
FAM/DEP/1050/2018 | 2018-08-06 | 2019-07-26 | FAM | 4 | 5 |  |  | NO |  | Others
IM/DEP/1105/2018 | 2018-08-02 | 2019-05-01 | IM | 4 | 6 |  |  | NO |  | Others
ENV/DEP/1089/2018 | 2018-09-10 | 2019-06-19 | ENV | 5 | 6 |  |  | NO |  | Others
SMC/DEP/1116/2018 | 2018-08-03 | 2019-05-05 | SMC | 5 | 6 |  |  | Yes('01-APR-2019') |  | Others
SMC/BU/1117/2018 | 2018-08-02 | 2019-02-17 | SMC | 7 | 7.3 |  |  | NO |  | Others
CCM/DEP/1058/2018 | 2018-04-25 | 2019-03-10 | CCM | 2 | 5 |  |  | NO |  | Others
ENV/BU/1090/2018 | 2018-08-06 | 2019-08-28 | ENV | 6 | 7 |  |  | NO |  | Others
FAM/TAP/1097/2018 | 2018-08-06 | 2019-08-28 | FAM | 5 | 6 |  |  | NO |  | Others
ENV/DEP/1091/2018 | 2018-07-27 | 2019-06-05 | ENV | 5 | 6 |  |  | NO |  | Others
PROD/BU/1080/2018 | 2018-05-30 | 2019-03-29 | PROD | 3 | 7.2 |  |  | NO |  | Others
PROD/DEP/1070/2018 | 2018-05-30 | 2019-09-30 | PROD | 3 | 6 |  |  | NO |  | Others
PROD/BU/1069/2018 | 2018-06-26 | 2019-04-25 | PROD | 6 | 8 |  |  | NO |  | Others
PROD/BU/1075/2018 | 2018-08-28 | 2019-06-26 | PROD | 7.1 | 7.3 |  |  | Yes('01-APR-2019') |  | Others
PROD/DEP/1076/2018 | 2018-09-10 | 2019-07-09 | PROD | 4 | 6 |  |  | Yes('01-APR-2019') |  | Others
NDTS/BU/1161/2018 | 2018-10-26 | 2019-07-04 | NDTS | 5 | 7.3 |  |  | NO |  | Others
SE/DEP/1066/2018 | 2018-05-30 | 2019-03-28 | SE | 3 | 5 |  |  | NO |  | Others
PA/BU/1129/2018 | 2019-02-08 | 2019-11-07 | PA | 7.1 | 8 |  |  | NO |  | Others
PROD/BU/1077/2018 | 2018-06-22 | 2019-04-20 | PROD | 6 | 7.1 |  |  | NO |  | Others
PA/BU/1131/2018 | 2018-09-19 | 2019-07-05 | PA | 7 | 8 |  |  | NO |  | Others
PROD/BU/1081/2018 | 2018-12-12 | 2019-10-10 | PROD | 6 | 7 |  |  | NO |  | Others
MCJ/DEP/1133/2018 | 2018-07-23 | 2019-05-08 | MCJ | 4 | 6 |  |  | NO |  | Others
MCJ/BU/1134/2018 | 2018-09-25 | 2019-06-28 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1162/2018 | 2018-10-31 | 2019-08-03 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1126/2018 | 2018-10-29 | 2019-08-01 | MCJ | 6 | 7.1 |  |  | NO |  | Others
MCJ/BU/1160/2018 | 2018-11-07 | 2019-08-23 | MCJ | 6 | 7.1 |  |  | NO |  | Others
MCJ/BU/1132/2018 | 2018-09-26 | 2020-02-11 | MCJ | 5 | 7 |  |  | NO |  | Others
MCJ/BU/1128/2018 | 2018-09-05 | 2019-06-08 | MCJ | 5 | 7.1 |  |  | NO |  | Others
PA/DEP/1135/2018 | 2018-09-10 | 2019-05-08 | PA | 5 | 7 |  |  | NO |  | Others
IM/DEP/1106/2018 | 2018-06-20 | 2019-02-24 | IM | 3 | 6 |  |  | NO |  | Others
PA/DEP/1138/2018 | 2018-09-10 | 2019-05-02 | PA | 5 | 7 |  |  | NO |  | Others
AGGLO/BU/1086/2018 | 2018-06-25 | 2019-04-25 | AGGLO | 3 | 6 |  |  | Yes('01-APR-2019') |  | Others
FAM/BU/1098/2018 | 2019-01-29 | 2019-11-17 | FAM | 3 | 6 |  |  | NO |  | Others
SMC/BU/1119/2018 | 2018-07-30 | 2019-04-28 | SMC | 7 | 7.3 |  |  | NO |  | Others
MCJ/BU/1163/2018 | 2018-10-11 | 2019-06-03 | MCJ | 5 | 7 |  |  | NO |  | Others
PA/DEP/1184/2018 | 2019-01-10 | 2019-06-20 | PA | 5 | 7.1 |  |  | NO |  | Others
PA/DEP/1136/2018 | 2018-10-03 | 2019-05-31 | PA | 5 | 7 |  |  | NO |  | Others
FAM/BU/1099/2018 | 2018-06-22 | 2019-07-14 | FAM | 3 | 5 |  |  | NO |  | Others
RM/BU/1112/2018 | 2018-07-23 | 2019-04-04 | RM | 4 | 7.1 |  |  | NO |  | Others
SMC/BU/1122/2018 | 2018-08-03 | 2019-01-18 | SMC | 7 | 7.2 |  |  | NO |  | Others
ENV/BU/1093/2018 | 2018-07-19 | 2019-05-07 | ENV | 5 | 6 |  |  | NO |  | Others
ENV/BU/1094/2018 | 2018-08-28 | 2019-06-16 | ENV | 6 | 7 |  |  | NO |  | Others
SE/DEP/1178/2018 | 2018-12-24 | 2019-04-14 | SE | 3 | 5 |  |  | NO |  | Others
IM/BU/1107/2018 | 2018-07-02 | 2019-03-08 | IM | 7.1 | 7.3 |  |  | NO |  | Others
ENV/BU/1152/2018 | 2018-12-17 | 2019-08-19 | ENV | 5 | 6 |  |  | NO |  | Others
PA/DEP/1139/2018 | 2018-08-03 | 2019-03-25 | PA | 5 | 7 |  |  | NO |  | Others
PA/DEP/1140/2018 | 2018-09-10 | 2019-05-02 | PA | 3 | 5 |  |  | NO |  | Others
SMC/BU/1123/2018 | 2018-07-06 | 2018-12-21 | SMC | 7 | 7.2 |  |  | NO |  | Others
SE/BU/1179/2018 | 2019-01-18 | 2019-04-27 | SE | 5 | 7.2 |  |  | NO |  | Others
FAM/BU/1100/2018 | 2018-08-06 | 2019-05-30 | FAM | 3 | 6 |  |  | NO |  | Others
IM/BU/1108/2018 | 2018-08-12 | 2019-04-18 | IM | 4 | 6 |  |  | NO |  | Others
ENV/BU/1095/2018 | 2018-07-24 | 2019-04-11 | ENV | 7 | 8 |  |  | NO |  | Others
AGGLO/DEP/1088/2018 | 2018-07-01 | 2019-03-31 | AGGLO | 3 | 5 |  |  | Yes('01-APR-2019') |  | Others
RM/BU/1111/2018 | 2018-07-20 | 2019-04-19 | RM | 4 | 7 |  |  | NO |  | Others
RM/BU/1113/2018 | 2018-08-02 | 2019-04-17 | RM | 5 | 7.1 |  |  | NO |  | Others
FAM/BU/1101/2018 | 2018-06-22 | 2019-04-10 | FAM | 3 | 7.1 |  |  | NO |  | Others
FAM/DEP/1102/2018 | 2018-07-19 | 2019-05-07 | FAM | 2 | 5 |  |  | NO |  | Others
SMC/BU/1173/2018 | 2019-01-31 | 2019-06-14 | SMC | 6 | 7 |  |  | NO |  | Others
MWJ/BU/1166/2018 | 2018-10-11 | 2019-04-12 | MWJ | 7 | 7.3 |  |  | NO |  | Others
PROD/DEP/1146/2018 | 2018-10-15 | 2019-05-15 | PROD | 2 | 5 |  |  | NO |  | Others
PROD/BU/1145/2018 | 2018-10-05 | 2019-05-12 | PROD | 3 | 6 |  |  | NO |  | Others
AGGLO/DEP/1154/2018 | 2018-10-15 | 2019-08-14 | AGGLO | 3 | 5 |  |  | NO |  | Others
CCM/BU/1156/2018 | 2018-10-12 | 2019-04-27 | CCM | 4 | 7.1 |  |  | NO |  | Others
PA/DEP/1141/2018 | 2018-10-03 | 2019-04-24 | PA | 5 | 7.1 |  |  | NO |  | Others
SMC/BU/1150/2018 | 2018-10-22 | 2019-07-21 | SMC | 6 | 6 |  |  | NO |  | Others
MWJ/BU/1167/2018 | 2018-10-23 | 2019-05-07 | MWJ | 5 | 7 |  |  | NO |  | Others
SE/TAP/1168/2018 | 2018-10-15 | 2019-10-02 | SE | 6 | 7.3 |  |  | NO |  | Others
SE/DEP/1169/2018 | 2018-12-24 | 2019-12-23 | SE | 3 | 5 |  |  | NO |  | Others
FAM/DEP/1143/2018 | 2018-10-05 | 2019-05-26 | FAM | 2 | 5 |  |  | NO |  | Others
FAM/BU/1157/2018 | 2018-12-03 | 2019-07-19 | FAM | 2 | 6 |  |  | NO |  | Others
CCM/BU/1158/2018 | 2018-09-20 | 2019-09-05 | CCM | 2 | 6 |  |  | NO |  | Others
SMC/BU/1149/2018 | 2018-10-09 | 2019-04-10 | SMC | 7.1 | 7.2 |  |  | NO |  | Others
ENV/BU/1155/2018 | 2018-09-26 | 2019-12-25 | ENV | 7 | 7.3 |  |  | NO |  | Others
PROD/BU/1187/2019 | 2019-02-08 | 2019-05-21 | PROD | 6 | 7 |  |  | NO |  | Others
IM/BU/1147/2018 | 2019-03-20 | 2019-09-01 | IM | 7.3 | 8 |  |  | NO |  | Others
SE/DEP/1174/2018 | 2019-03-04 | 2020-05-23 | SE | 1 | 3 |  |  | NO |  | Others
CCM/DEP/1172/2018 | 2019-01-01 | 2020-01-31 | CCM | 1 | 5 |  |  | NO |  | Others
MC/DEP/1176/2018 | 2018-12-24 | 2019-10-24 | MC | 3 | 5 |  |  | NO |  | Others
RC/DEP/540/2014 | 2015-02-03 | 2016-05-31 | RM | 4 | 5 |  |  | NO |  | RAW MATERIALS BENEFICIATION AND FERRO ALLOYS

## FY19-Started-FY19-Completed
Project Number | Actual SD | Revised ED | Group | TRL From | TRL To | Actual TRL From | Actual TRL To | Completed on | Closed On | Program Area | Avg PPI
SMC/BU/1011/2018 | 2018-04-24 | 2018-07-27 | SMC | 7 | 7.2 | 7 | 7.2 | 2018-08-02 | 2018-11-28 | Others | 100
IM/BU/1059/2018 | 2018-05-02 | 2019-02-28 | IM | 4 | 7.1 | 4 | 8 | 2019-03-20 | 2019-03-22 | Others | 90
SE/BU/1065/2018 | 2018-05-21 | 2019-03-28 | SE | 2 | 5 | 2 | 8 | 2019-02-26 | 2019-04-04 | Others | 95
SE/BU/1014/2018 | 2018-06-11 | 2019-04-18 | SE | 2 | 7 | 2 | 6 | 2019-02-26 | 2019-04-04 | Others | 97
AGGLO/TAP/1031/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 90
AGGLO/TAP/1045/2018 | 2018-05-30 | 2019-05-14 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-15 | 2019-02-18 | Others | 100
AGGLO/DEP/1053/2018 | 2018-06-04 | 2019-02-18 | AGGLO | 2 | 6 | 2 | 6 | 2019-02-18 | 2019-02-19 | Others | 95
IM/BU/1061/2018 | 2018-06-07 | 2019-03-23 | IM | 7 | 8 | 4 | 7 | 2019-03-19 | 2019-03-20 | Others | 100
AGGLO/DEP/1057/2018 | 2018-05-30 | 2019-02-13 | AGGLO | 2 | 3 | 2 | 3 | 2019-02-13 | 2019-02-18 | Others | 95
IM/BU/1060/2018 | 2018-05-02 | 2019-02-15 | IM | 4 | 6 | 4 | 6 | 2019-03-19 | 2019-03-20 | Others | 97
ENV/BU/1092/2018 | 2018-07-24 | 2019-02-11 | ENV | 7 | 8 | 4 | 7 | 2019-02-10 | 2019-02-12 | Others | 95
AGGLO/TAP/1087/2018 | 2018-06-20 | 2019-04-05 | AGGLO | 3 | 5 | 3 | 5 | 2019-02-15 | 2019-02-18 | Others | 100
ENV/TAP/1148/2018 | 2018-12-07 | 2020-06-08 | ENV | 6 | 7 | 4 | 7.1 | 2019-02-12 | 2019-02-15 | Others | 100
SE/BU/997/2017 | 2018-07-24 | 2019-02-06 | SE | 7.1 | 7.3 |  |  | Yes('26-FEB-2019') |  | Others
SMC/BU/962/2017 | 2018-05-28 | 2019-01-25 | SMC | 6 | 6 |  |  | Yes('06-MAR-2019') |  | Others
NDTS/DEP/1071/2018 | 2018-06-04 | 2019-04-05 | NDTS | 3 | 7.1 | 3 | 7.2 | Yes('22-FEB-2019') |  | Others
ENV/DEP/1024/2018 | 2018-05-23 | 2019-05-18 | ENV | 4 | 6 |  |  | Yes('27-MAR-2019') |  | Others
ENV/DEP/1027/2018 | 2018-05-30 | 2019-05-20 | ENV | 3 | 5 |  |  | Yes('25-MAR-2019') |  | Others
IM/BU/1104/2018 | 2018-09-11 | 2019-05-18 | IM | 7.1 | 7.3 |  |  | Yes('21-MAR-2019') |  | Others
SMC/BU/1114/2018 | 2018-06-27 | 2019-03-28 | SMC | 7.1 | 7.3 |  |  | Yes('04-MAR-2019') |  | Others
SMC/DEP/1142/2018 | 2018-10-31 | 2019-04-17 | SMC | 6 | 6 |  |  | Yes('28-MAR-2019') |  | Others
SE/BU/1067/2018 | 2018-05-21 | 2019-03-19 | SE | 2 | 6 | 2 | 6 | Yes('26-FEB-2019') |  | Others
SMC/BU/1118/2018 | 2018-07-06 | 2019-02-21 | SMC | 7 | 7.3 |  |  | Yes('06-MAR-2019') |  | Others
PROD/DEP/1074/2018 | 2018-05-30 | 2019-03-28 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others
ENV/BU/1096/2018 | 2018-06-20 | 2019-04-05 | ENV | 6 | 7 | 7.1 | 7.3 | Yes('07-FEB-2019') |  | Others
SMC/BU/1120/2018 | 2018-07-17 | 2019-01-01 | SMC | 7 | 7.3 | 7 | 7.2 | Yes('06-FEB-2019') |  | Others
PROD/DEP/1144/2018 | 2018-10-03 | 2019-05-10 | PROD | 5 | 7 |  |  | Yes('30-MAR-2019') |  | Others